## Sheet1
| GTO - LIST OF ITEMS | [16 empty] | Contrato: ICN_SBR | Gerado em 27/7/2026 às 11:52
Context | Item | Certificate | Updated Status | Original Jx | Actual Jx | Description | Bigram | Nº + Description | InspType | Proof Reference | Performance | Mode | Status | Hull Passage | Hull Passage Parts | Position AC | Type
SBR4 | 2 | Test HP2C | 4 - Under Analysis | J01 & J03 | J06 | Broadcasting safety alarms to all rooms of the ship. | HP | 09 - Coordinate damage control | HCT |  | Broadcasting Safety alarm from Main Safety Office (Control room) to all rooms of the ship. In the case the Main Safety Office is outside the submarine, a communication mean between the Main Safety Office and the Control room is required. | Not applicable | Partial
SBR4 | 39 | S02 BBZ0006 | 1 - Validated by ICN | J01 & J03 | J06 | Aft battery room: BB00060 - Leak test: Fitted room (0.2bar). | BB | 13 - Confine the hazardous areas | PTRH |  | Confine the battery rooms | Local (manual) | Partial (only battery rooms).
SBR4 | 49 | S02 BBZ0007 | 1 - Validated by ICN | J01 & J03 | J06 | Forward battery room: BB00070: Leak test: Fitted room (0.2bar). | BB | 13 - Confine the hazardous areas | PTRH |  | Confine the battery rooms | Local (manual) | Partial (only battery rooms).
SBR4 | 133 | Test BF1C | 1 - Validated by ICN | J01 & J03 | J06 | Functional test | BF | 20 - Electric supply | STW |  | 1. 115V/60Hz normal Shore Power Supply: - An independent backup power supply is able to replace the normal power supply in less than 10 minutes. 2. Supply from onboard 115V / 60 Hz converters. | Local | Partial
SBR4 | 207 | S02 EVZ0002 | 2 - Not Blocking | J02 & J04 | J06 | EV Water cooling circuit (battery). Leak test. | EV | 20 - Electric supply | PTRH |  | Availability of ancillaries needed. | Not applicable | Nominal
SBR4 | 208 | S02 BBZ0001 | 1 - Validated by ICN | J02 & J04 | J06 | BB Water cooling circuit. Distilled water circuit. Leak test: circuit to batteries. | BB | 20 - Electric supply | PTRH |  | Availability of ancillaries needed. | Not applicable | Nominal
SBR4 | 209 | S02 BBZ0004 | 1 - Validated by ICN | J02 & J04 | J06 | BB Water cooling circuit. Leak test: aft battery. | BB | 20 - Electric supply | PTRH |  | Availability of ancillaries needed. | Not applicable | Nominal
SBR4 | 211 | S02 BBZ0008 | 3 - Blocking | J02 & J04 | J06 | Electrolyte agitation circuit. Leak test. | BB | 20 - Electric supply | PTRH |  | Availability of ancillaries needed. | Not applicable | Nominal
SBR4 | 214 | Test BB1C partial Elementary nº1 | 1 - Validated by ICN | J02 & J04 | J06 | Electrolyte agitation system. | BB | 20 - Electric supply | STW |  | Availability of ancillaries needed. | Not applicable | Nominal
SBR4 | 243 | S02 BBZ0005 | 1 - Validated by ICN | J02 & J04 | J06 | BB Water cooling circuit. Leak test: forward battery. | BB | 20 - Electric supply | PTRH |  | Availability of ancillaries needed. | Not applicable | Nominal
SBR4 | 326 | S02 EFZ0002 | 1 - Validated by ICN | J05 (J06Cer) | J06 | Firefighting electric pump Leak pressure test of the water mist feed circuit to the diesel diffusers | EF | 14 - Fight the fire | PTRH |  | Fire fighting in diesel compartment | Local (fromEF02503) | Partial
SBR4 | 405 | Shipyard report (BIC report) - J06 | 5 - Waiting Proof | J06 | J06 | Water tightness mastered status according to procedure of the hull watertightness management for submarine [R3], including ¿ Onboard inspection part: The Hull Watertightness Manager must be present during the inspection with the BIC report to cross check the situation with the Watch and Operation Team. Cross check requirements: - Actual Circuit status is consistent with circuit status in the BIC report (especially absence of not declared works); - Counterfoil booklet status is consistent with the actual circuit status; - In case of specific provisions (including restriction devices) defined by the BIC report, they are implemented on board. (description and visual check to be reported). ¿ Identification of works from last safety milestones and traceability folder. | Several | 99 - Several | Shipyard prerequisites |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 406 | S02 BMZ0001 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure Leak test | BD;BM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 407 | S02 BMZ0002 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure Leak test | BD;BM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 408 | S02 BMZ0003 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure Leak test | BD;BM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 409 | S02 BMZ0004 | 5 - Waiting Proof | J06 | J06 | Circuits subjected to submergence pressure Leak test | BD;BM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 411 | S02 DMZ0001 | 1 - Validated by ICN | J06 | J06 | Leak test. Circuits subjected to submergence Circuits subjected to submergence pressure. | DA;DM;DN | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 412 | S02 DMZ0002 | 5 - Waiting Proof | J06 | J06 | Leak test. Circuits subjected to submergence Circuits subjected to submergence pressure. | DA;DM;DN | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 415 | S02 DNZ0001 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test | DN | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity | Local
SBR4 | 416 | S02 DNZ0002 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test | DN | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity | Local
SBR4 | 417 | S02 DNZ0003 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test | DN | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity | Local
SBR4 | 426 | S02 EMZ0003 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Entire EM circuit | EM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 432 | S02 ENZ0003 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Entire EN circuit | EN | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 434 | S02 KTZ0001 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 435 | S02 KTZ0002 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 436 | S02 KTZ0003 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 437 | S02 KTZ0004 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 438 | S02 KTZ0005 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 439 | S02 KTZ0006 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 442 | S02 KTZ0009 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the draining circuit of tube | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 443 | S02 KTZ0010 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the draining circuit of tube | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 445 | S02 KTZ0012 | 4 - Under Analysis | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the draining circuit of tube | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 446 | S02 KTZ0013 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the circuit upstream of the equalizing valves | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 447 | S02 KTZ0014 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the circuit upstream of the equalizing valves | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 451 | S02 MBZ0001 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test | MB | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 461 | Test DA1C Elementary test 1 Local mode and DSP | 1 - Validated by ICN | J06 | J06 | Setting to work of bilge draining system Check the water volumes of draining tanks Table 1 and 2 | DA;OO | 02 - Detect a flooding | STW |  | Detect a flooding | Remote (PSP) | Partial (defect and incident levels)
SBR4 | 462 | Test DA1C Elementary test 2 | 1 - Validated by ICN | J06 | J06 | Setting to work of bilge draining system Check the volume of the bilges Table 3 | DA;OO | 02 - Detect a flooding | STW |  | Detect a flooding | Remote (PSP) | Partial (defect and incident levels)
SBR4 | 463 | Test DA1C Elementary test 3 at least DSP | 1 - Validated by ICN | J06 | J06 | Setting to work of bilge draining system Low, Incident and defect level for all tanks and bilges Table 4 and 5 | DA;OO | 02 - Detect a flooding | STW |  | Detect a flooding | Remote (PSP) | Partial (defect and incident levels)
SBR4 | 487 | S02 DBZ0002 | 1 - Validated by ICN | J06 | J06 | Leak test. Circuits subjected to submergence pressure. | DB;OO | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity | Local | Available for sailing / Unavailable for sailing
SBR4 | 494 | S02 DB00601 | 3 - Blocking | J06 | J06 | Leak test. Circuits subjected to submergence pressure. | DB;OO | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity | Local | Available for sailing / Unavailable for sailing
SBR4 | 526 | Test DB1C partial Elementary n°1 | 1 - Validated by ICN | J06 | J06 | Functional test of vent valves in local control checking of the vent valves and the manual distributor. | DB;OO | 07 - Lighten the submarine | STW |  | To keep the buoyancy in surface | Remote | Nominal
SBR4 | 528 | Test DB2C | 2 - Not Blocking | J06 | J06 | Drain valves & circuits tightness test over 24 hours Important: Test to be done just after the setting afloat. If not satisfactory, the ship shall be brought back in drydock. | DB;OO | 07 - Lighten the submarine | HCT |  | To keep the buoyancy in surface | Remote | Nominal
SBR4 | 560 | Shipyard certificate Communication between quayside and the submarine - J06 | 4 - Under Analysis | J06 | J06 | Communication between quayside and the submarine | HG;HP | 09 - Coordinate damage control | Shipyard prerequisites |  | To communicate with the quayside from the submarine. Intercommunicate between all the rooms of the submarine and the control room. General orders and alarms broadcasting network. | Not applicable | Partial
SBR4 | 564 | Test BE1C partial Elementary n°1 | 4 - Under Analysis To Not Blocking | J06 | J06 | Test for the correct functioning of the emergency lighting network | BE | 11 - Emergency lighting | STW |  | Emergency lighting and normal lighting supplied by independent electrical networks | Not applicable | Partial (only battery rooms)
SBR4 | 566 | Trial EF 6 At least local and DSP | 1 - Validated by ICN | J06 | J06 | Good functioning of the fire detection. | EF | 12 - Detect a fire | HAT |  | Fire detection in the submarine (all smoke & flame sensors) | Local (Firefighting panel) + synthesis remotely sent to the Main Safety Office | Partial
SBR4 | 570 | Test EF2C partial Elementary n°1 Table 1 & 2 | 1 - Validated by ICN | J06 | J06 | Running test - Water mist system – Local and remote control and monitoring | EF;EJ;OO | 14 - Fight the fire | STW |  | Firefighting in electrical switchboards and battery rooms. Firefighting in diesel compartment | Remote (from DSP) | Partial
SBR4 | 571 | Trial EF2 | 1 - Validated by ICN | J06 | J06 | Functional trial of fixed firefighting sub system. | EF;EJ;OO | 14 - Fight the fire | HAT |  | Firefighting in electrical switchboards and battery rooms. Firefighting in diesel compartment | Remote (from DSP) | Partial
SBR4 | 575 | Test FR2C partial Elementary n°1 table 2 | 1 - Validated by ICN | J06 | J06 | Gas analysers (O2, CO, CO2) Functional tests. | FR | 16 - Detect an anomaly in atmosphere composition | STW |  | To detect an anomaly in atmosphere composition | Local / Remote (From CSP) | Partial
SBR4 | 585 | E01 BS02507 | 1 - Validated by ICN | J06 | J06 | Switchboard safety. Assembly, connecting and grounding. | BS | 20 - Electric supply | AIS |  | Supply emergency in case of loss of main electrical supply. | Local | Partial
SBR4 | 605 | FH2C | 4 - Under Analysis To Not Blocking | J06 | J06 | Air renewal ventilation system : Configurations ventilation charts in battery rooms | BH;FH;OO | 24 - Ventilate the ship | HCT |  | To ventilate the ship in the different configurations: - Surface, quayside and snorkel; - With and without battery charging. To report to the Control Room: - Availability of the ventilation (loss of flow rate and pressure), - Position Open/Closed of the battery ventilation valves. Note: Ensure that the ship ventilation works properly after the launching of the submarine. | Local / Remote (monitoring from CSP). | Partial
SBR4 | 607 | Test FR2C partial Elementary n°1 table 2 (Local and remote mode) | 1 - Validated by ICN | J06 | J06 | Gas analysers (H2). Functional tests. | FR | 25 - Detect hydrogen anomaly | STW |  | To report the hydrogen alarms to the Control room. | Remote (From CSP)
SBR4 | 609 | B05 AC30001 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30001 | AC;MB | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30001 | AC30001 ; MB00003-1 ; MB00003-2 ; MB00003-3 ; MB00004 ; MB00312 ; MB00300 ; MB00301 | under water line | 15
SBR4 | 610 | B05 AC30005 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30005 | AC;FP | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30005 | AC30005 ; FP00100 ; FP00101 ; FP00102 ; FP00103 ; FP00104 ; FP00105 | under water line | 12
SBR4 | 611 | B05 AC30010 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30010 | AC;AG | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30010 | AC30010 ; AG00001 | between water line and water line + 1 m | 23
SBR4 | 612 | B05 AC30020 | 2 - Not Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30020 | AC;AG | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30020 | AC30020 ; AG00002 | between water line and water line + 1 m | 23
SBR4 | 613 | B05 AC30030 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30030 | AC;AG | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30030 | AC30030 ; AG00013 ; AG00023 ; AG00033 ; AG00053 | above water line + 1 meter | 24
SBR4 | 614 | B05 AC30040 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30040 | AC;AG | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30040 | AC30040 ; AG00014 ; AG00024 ; AG00034 | between water line and water line + 1 m | 24
SBR4 | 616 | B05 AC30051 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30051 | AC;BH | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30051 | AC30051 ; BH00001 ; BH00002 | above water line + 1 meter | 0
SBR4 | 618 | B05 AC30053 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30053 | AC;AG;HL | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30053 | AC30053 ; AG00055 ; HL40053 ; HL22102D | between water line and water line + 1 m | AG: 23 HL: 20
SBR4 | 619 | B05 AC30060 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30060 | AC;GS;RM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30060 | AC30060 ; RM00237 ; RM00007 ; RM00217 ; RM00207 ; GS02505 ; RM00017 ; RM50057R ; RM00057 ; RM50107M ; RM00147 ; RM50017R ; RM00157 ; RM50027R ; RM00247 ; RM50127R ; RM00257 ; RM50097R ; RM00267 ; RM50087R ; RM00497 ; RM50117M ; RM00167 ; RM50067X | between water line and water line + 1 m | 17
SBR4 | 620 | B05 AC30070 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30070 | AC;AG | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30070 | AC30070 ; AG00016 ; AG00026 ; AG00036 | between water line and water line + 1 m | 24
SBR4 | 621 | B05 AC30071 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30071 | AC;AG | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30071 | AC30071 ; AG00017 ; AG00027 ; AG00037 ; AG00057 ; AG00077 | above water line + 1 meter | 24
SBR4 | 622 | B05 AC30080 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30080 | AC;AG;HL | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30080 | AC30080 ; AG00008 ; HL40080 ; HL22100D ; HL22102D ; HL22103D ; HL22104D ; HL22105D ; HL22124D | between water line and water line + 1 m | AG: 23 HL: 20
SBR4 | 623 | B05 AC30090 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30090 | AC;AG | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30090 | AC30090 ; AG00019 ; AG00029 ; AG00039 | between water line and water line + 1 m | 24
SBR4 | 624 | B05 AC30101 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30101 | AC;KT | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30101 | AC30101 ; KT00251 ; KT03611 ; KT00551 ; KT00651 ; KT00351 ; KT00451 ; KT03721-1 ; KT03721-2 ; KT01351 ; KT03411 ; KT01111 ; KT01411 ; KT03911 ; KTXXXX ; KT00751 ; KT01051 ; KT01451 ; KT01461 ; KT01A51 ; KT01C51 ; KT01B51 ; KT01D51 ; KT40001 ; KT50581R ; | under water line | 11
SBR4 | 625 | B05 AC30102 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30102 | AC;KT | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30102 | AC30102 ; KT00252 ; KT03612 ; KT00552 ; KT00652 ; KT00352 ; KT00452 ; KT03722-1 ; KT03722-2 ; KT01352 ; KT03412 ; KT01112 ; KT01412 ; KT03912 ; KTXXXX ; KT00752 ; KT1052 ; KT01452 ; KT01462 ; KT01A52 ; KT01C52 ; KT01B52 ; KT01D52 ; KT40002 ; KT50582R ; | under water line | 11
SBR4 | 626 | B05 AC30103 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30103 | AC;KT | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30103 | AC30103 ; KT00253 ; KT03613 ; KT00553 ; KT00653 ; KT00353 ; KT00453 ; KT01353 ; KT03413 ; KT01113 ; KT01413 ; KT03913 ; KTXXXX ; KT01453 ; KT01463 ; KT00753 ; KT01053 ; KT01A53 ; KT01C53 ; KT40003 ; KT50583R ; KT06C43 ; KT50483R ; KT07C43 ; KT54583R ; | under water line | 11
SBR4 | 627 | B05 AC30104 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30104 | AC;KT | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30104 | AC30104 ; KT00254 ; KT03614 ; KT00554 ; KT00654 ; KT00354 ; KT00454 ; KT01354 ; KT03414 ; KT01114 ; KT01414 ; KT03914 ; KTXXXX ; KT01454 ; KT01464 ; KT00754 ; KT01054 ; KT01A54 ; KT01C54 ; KT40004 ; KT50584R ; KT06C44 ; KT50484R ; KT07C44 ; KT54584R ; | under water line | 11
SBR4 | 628 | B05 AC30105 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30105 | AC;KT | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30105 | AC30105 ; KT00255 ; KT03615 ; KT00555 ; KT00655 ; KT00355 ; KT00455 ; KT01355 ; KT03415 ; KT01115 ; KT01415 ; KT03915 ; KTXXXX ; KT01455 ; KT01465 ; KT00755 ; KT01055 ; KT01A55 ; KT01C55 ; KT40005 ; KT50585R ; KT06C45 ; KT50485R ; KT07C45 ; KT54585R ; | under water line | 11
SBR4 | 629 | B05 AC30106 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC30106 | AC;KT | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC30106 | AC30106 ; KT00256 ; KT03616 ; KT00556 ; KT00656 ; KT00356 ; KT00456 ; KT01356 ; KT03416 ; KT01116 ; KT01416 ; KT03916 ; KTXXXX ; KT01456 ; KT01466 ; KT00756 ; KT01056 ; KT01A56 ; KT01C56 ; KT40006 ; KT50586R ; KT06C46 ; KT50486R ; KT07C46 ; KT54586R ; | under water line | 11
SBR4 | 636 | B05 AC31014 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC31014 - Lubricating oil supply EL00006 | AC;EL | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC31014 | AC31014 ; EL00007 ; EL00006 ; EL50001L | between water line and water line + 1 m | 13
SBR4 | 638 | B05 AC31016 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC31016 | AC;DY | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC31016 | AC31016 ; AC41016 ; DY00908 ; DY00909 ; DY00910 ; DY51000Y ; DY51001Y | between water line and water line + 1 m | 13
SBR4 | 645 | B05 AC32002 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32002 - Diesel supply EG00101 (diesel) | AC;EG | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32002 | AC32002 ; EG00102 ; EG00101 ; EG50100G1 ; EG50100G2 | between water line and water line + 1 m | 13
SBR4 | 646 | B05 AC32003 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32003 - Diesel supply EQ00411 (água) | AC;EG;EQ | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32003 | AC32003 ; EG00202 ; EQ00411 ; EG50200M | between water line and water line + 1 m | 13
SBR4 | 647 | B05 AC32004 | 6 - Waiting B05 | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32004 | AC;BM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32004 | AC32004 ; BM00041 ; BM00046 | under water line | 1
SBR4 | 648 | B05 AC32005 | 6 - Waiting B05 | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32005 | AC;BM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32005 | AC32005 ; BM00040 ; BM00042 ; BM00175 ; BM50176Y ; BM00072 | under water line | 3
SBR4 | 649 | B05 AC32006 | 6 - Waiting B05 | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32006 | AC;BM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32006 | AC32006 ; BM00038 | under water line | 1
SBR4 | 650 | B05 AC32007 | 6 - Waiting B05 | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32007 | AC;BM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32007 | AC32007 ; BM00031 ; BM00032 ; BM00176 ; BM50103Y ; BM00073 | under water line | 3
SBR4 | 651 | B05 AC32008 | 6 - Waiting B05 | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32008 | AC;BM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32008 | AC32008 ; BM00011 ; BM00016 | under water line | 1
SBR4 | 652 | B05 AC32009 | 6 - Waiting B05 | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32009 | AC;BM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32009 | AC32009 ; BM00010 ; BM00012 ; BM00202 ; BM50101Y ; BM00172 | under water line | 3
SBR4 | 653 | B05 AC32010 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32010 | AC;UL | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32010 | AC32010 ; UL00001 ; UL00111 ; UL00010 ; UL00011 ; UL00012 ; UL00013 ; UL00113 ; UL00112 | between water line and water line + 1 m | 12
SBR4 | 654 | B05 AC32011 | 6 - Waiting B05 | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32011 | AC;BM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32011 | AC32011 ; BM00001 ; BM00002 ; BM00201 ; BM50100Y ; BM00173 | under water line | 3
SBR4 | 655 | B05 AC32012 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32012 | AC;DN | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32012 | AC32012 ; DN00111 ; DN00112 ; DN00141 ; DN50142Y ; DN00142 | under water line | 3
SBR4 | 657 | B05 AC32014 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32014 | AC;FQ | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32014 | AC32014 ; FQ00101 ; FQ00102 | under water line | 5
SBR4 | 658 | B05 AC32015 | 6 - Waiting B05 | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32015 | AC;BM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32015 | AC32015 ; BM00007 ; BM00008 | under water line | 1
SBR4 | 660 | B05 AC32023 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32023 | AC;BQ | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32023 | AC32023 ; BQ00001 ; BQ22023 ; BQ50005E ; BQ20001 ; BQ50007E ; BQ22025 ; BQ50147E ; BQ00077 ; BQ50009E1 ; BQ50009E2 ; BQ50009E3 ; BQ00005 | between water line and water line + 1 m | 19
SBR4 | 661 | B05 AC32024 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32024 | AC;BQ | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32024 | AC32024 ; BQ00002 ; BQ22024 ; BQ50006E ; BQ20002 ; BQ50008E ; BQ22026 ; BQ50146E ; BQ00098 ; BQ50010E1 ; BQ50010E2 ; BQ50010E3 ; BQ00006 | between water line and water line + 1 m | 19
SBR4 | 667 | B05 AC32030 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32030 | AC;BQ | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32030 | AC32030 ; BQ00015 | between water line and water line + 1 m | 22
SBR4 | 673 | B05 AC32038 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32038 - Water supply EQ00412 | AC;EJ;EQ | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32038 | AC32038 ; EJ00107 ; EJ50031J ; EQ00412 | between water line and water line + 1 m | 13
SBR4 | 676 | B05 AC32050 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32050 - Sanitary tank FQ00804 | AC;FQ | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32050 | AC32050 ; FQ00804 ; FQ50803A ; FQ00803 | under water line | 13
SBR4 | 704 | B05 AC33000 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33000 | AC;DM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33000 | AC33000 ; DM00004 ; DM00005 ; DM00032 ; DM52000Y ; DM00033 | under water line | 1
SBR4 | 705 | B05 AC33001 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33001 | AC;DM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33001 | AC33001 ; DM00013 ; DM00014 | under water line | 1
SBR4 | 706 | B05 AC33002 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33002 | AC;DN | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33002 | AC33002 ; DN00311 ; DN00312 ; DN00341 ; DN50342Y ; DN00342 | under water line | 3
SBR4 | 708 | B05 AC33004 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33004 | AC;BH | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33004 | AC33004 ; AC43004 ; ER00033 ; ER50118X ; ER00034 ; ER50119X ; BH00062 ; BH50060X ; BH00061 | between water line and water line + 1 m | 8
SBR4 | 711 | B05 AC33009 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33009 | AC;BH;EQ | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33009 | AC33009 ; AC43009 ; BH00012 ; BH50003Y ; EQ00110 ; EQ50106Y | between water line and water line + 1 m | 8
SBR4 | 714 | B05 AC33012 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33012 | AC;BH | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33012 | AC33012 ; AC43012 ; BH00035 ; BH50034Y ; BH00036 ; BH50041R ; BH00040 ; BH50045R | between water line and water line + 1 m | 8
SBR4 | 718 | B05 AC33018 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33018 | AC;BH | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33018 | AC33018 ; BH00102 ; BH00105 ; BH50073M | between water line and water line + 1 m | 2
SBR4 | 719 | B05 AC33019 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33019 | AC;BH | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33019 | AC33019 ; BH00103 ; BH00106 | between water line and water line + 1 m | 1
SBR4 | 725 | B05 AC33028 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33028 | AC;BE;HE;OO;UN | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33028 | AC33028 ; AC43028 ; OO22510R ; BE27100I ; UN22800D ; HE22500R | between water line and water line + 1 m | 20
SBR4 | 729 | B05 AC33043 | 6 - Waiting B05 | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33043 | AC;HP | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33043 | AC33043 ; HP00001 ; HP00002 ; HP00003 ; HP50002M ; HP50002M1-1 ; HP50002M1-2 ; HP50004M | between water line and water line + 1 m | 4
SBR4 | 730 | B05 AC33050 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33050 | AC;RM | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33050 | AC33050 ; RM00018 ; RM00078 ; RM50048M ; RM00088 ; RM00218 ; RM50018R ; RM00098 ; RM50028R | between water line and water line + 1 m | 17
SBR4 | 732 | B05 AC33052 | 2 - Not Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33052 | AC;KL | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33052 | AC33052 ; AC43052 ; KL20100D ; KL20200D | between water line and water line + 1 m | 20
SBR4 | 733 | B05 AC33053 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33053 | AC;RD;RH | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33053 | AC33053 ; AC43053 ; RD ; RD ; RH ; RH | between water line and water line + 1 m | 21
SBR4 | 736 | B05 AC33056 | 7 - Missing Vacuum Test or Sign | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33056 | AC;UE | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33056 | AC33056 ; AC43056 ; UE24400D ; UE22000D | between water line and water line + 1 m | 20
SBR4 | 743 | B05 AC33064 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC33064 | AC;RF | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC33064 | AC33064 ; AC43064 ; RF00008 ; RF00007 ; RF00004 | between water line and water line + 1 m | 14
SBR4 | 751 | B05 AC34024 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC34024 | AC;KT | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC34024 | AC34024 ; KT01418 ; KT03518 ; KT00718 ; KT50328Y ; KT00818 | under water line | 3
SBR4 | 752 | B05 AC34025 | 1 - Validated by ICN | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC34025 | AC;KT | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC34025 | AC34025 ; KT01417 ; KT03517 ; KT00717 ; KT50327Y ; KT00817 | under water line | 3
SBR4 | 756 | B05 AC34030 | 3 - Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC34030 | AC;BE;HL | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC34030 | AC34030 ; AC44030 ; BE ; HL44030 ; HL22103D | above water line + 1 meter | 21
SBR4 | 764 | B05 AC34040 | 2 - Not Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC34040 | AC;EX | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC34040 | AC34040 ; AC44040 ; EX50023Y ; EX00107 ; EX50074R ; EX00179 ; EX50066R ; EX00160 ; EX50051R ; EX00177 | between water line and water line + 1 m | 8
SBR4 | 765 | B05 AC34041 | 2 - Not Blocking | J06 | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC34041 | AC;EX | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC34041 | AC34041 ; AC44041 ; EX50099Y ; EX00108 ; EX50073R ; EX00178 ; EX50052R ; EX00175 ; EX50054R ; EX00176 | between water line and water line + 1 m | 8
SBR4 | 777 | Test AG1C | 1 - Validated by ICN | J06 | J06 | Hatches Functional test | AC | 36 - Pressure hull integrity | HCT |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local | Fitted / Provisionally blanked off |  | Closed
SBR4 | 779 | Test FQ1C partial Table 2 | 5 - Waiting Proof | J06 | J06 | Safety device Sewage tank FQ | AC | 36 - Pressure hull integrity | STW |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local | Fitted / Provisionally blanked off |  | Closed
SBR4 | 780 | Test UL0C partial Elementary 5 | 1 - Validated by ICN | J06 | J06 | Safety device Submerged signal ejector UL | AC | 36 - Pressure hull integrity | STW |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local | Fitted / Provisionally blanked off |  | Closed
SBR4 | 781 | Test KT4C | 5 - Waiting Proof | J06 | J06 | Safety device Torpedo tubes KT | AC | 36 - Pressure hull integrity | HCT |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local | Fitted / Provisionally blanked off |  | Closed
SBR4 | 782 | Shipyard report (BOC Report) - J06 | 5 - Waiting Proof | J06 | J06 | Water tightness monitoring Hull pressure integrity status according to the Procedure of the hull watertightness management for submarine SMB-360103 [R4] including 1- Onboard inspection part: The Hull Watertightness Manager must be present during the inspection with the BOC report to cross check the situation with the Watch and Operation Team. Cross check requirements: - Actual Circuit status is consistent with penetration status in the BOC report (especially absence of not declared works); - Counterfoil booklet status is consistent with the actual penetration status; - In case of specific provisions (including restriction devices) defined by the BOC report, they are implemented on board. (description and visual check to be eported). 2- Identification of works from last safety milestones and traceability folder. | AC | 36 - Pressure hull integrity | Shipyard prerequisites |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local | Fitted / Provisionally blanked off |  | Closed
SBR4 | 783 | Shipyard report (Garbage unit FP) - J06 | 1 - Validated by ICN | J06 | J06 | Safety device Garbage unit FP Safety checks are the following ones: 1- Impossibility to open the ball valve when the upper hatch is unlocked. 2- Impossibility to unlock the upper hatch when the ball valve is not completely shut. 3- Impossibility to unlock the upper hatch when the vent valve is shut | AC | 36 - Pressure hull integrity | Shipyard prerequisites |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local | Fitted / Provisionally blanked off |  | Closed
SBR4 | 784 | SHIP2C (General depression test on board) - J06 | 5 - Waiting Proof | J06 | J06 | General depression test on board - To be performed before every setting afloat | AC;BH | 36 - Pressure hull integrity | Shipyard prerequisites |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local | Fitted / Provisionally blanked off |  | Closed
SBR4 | 785 | Apply Submarine Operating Instructions (SOI) - J06 | 4 - Under Analysis | J06 | J06 | Document to be produce by ICN in conformity with SOI, This includes specifically SOD_M2_CH_1-14 “Refloating” | Several | 99 - Several | Shipyard prerequisites |  | Control & Monitoring
SBR4 | 786 | Main Safety Office is manned 24x7 by qualified personnel - J06 | 1 - Validated by ICN | J06 | J06 | Monitoring of the following alarms: Availability of the ventilation (loss of flow rate and pressure), Position Open/Closed of the battery ventilation valves, Fire detection, Hydrogen detection, Flooding detection. | Several | 99 - Several | Shipyard prerequisites |  | Control & Monitoring
SBR4 | 809 | Test HG1C Elementary n°1 and 2 - J06 | 4 - Under Analysis | J06 | J06 | Functional test of the voice-activated telephone network | HG;HP | 09 - Coordinate damage control | HCT |  | To communicate with the quayside from the submarine. Intercommunicate between all the rooms of the submarine and the control room. General orders and alarms broadcasting network. | Not applicable | Partial
SBR4 | 817 | S02 EZZ0001 | 1 - Validated by ICN | J06 | J06 | Leak pressure tests Aft air production and distribution line | EZ | 15 - Breathing air network | PTRH |  | To have breathing air network | local, monitoring remote (from DSP) | Nominal
SBR4 | 818 | S02 EZZ0002 | 3 - Blocking | J06 | J06 | Leak pressure tests Forward air production and distribution line | EZ | 15 - Breathing air network | PTRH |  | To have breathing air network | local, monitoring remote (from DSP) | Nominal
SBR4 | 820 | S08 EZZ0002 | 1 - Validated by ICN | J06 | J06 | Circuit conservation Forward air production and distribution line | EZ | 15 - Breathing air network | PTRH |  | To have breathing air network | local, monitoring remote (from DSP) | Nominal
SBR4 | 822 | S03 EZZ0002 | 1 - Validated by ICN | J06 | J06 | Verification of the free discharge Forward section | EZ | 15 - Breathing air network | PTRH |  | To have breathing air network | local, monitoring remote (from DSP) | Nominal
SBR4 | 840 | Test EZ2C | 1 - Validated by ICN | J06 | J06 | Functional tests of air network in harbour | EZ | 15 - Breathing air network | HCT |  | To have breathing air network | local, monitoring remote (from DSP) | Nominal
SBR4 | 855 | Test FH3C Partial Table 4, 5, 6, 7, 8 and 9 | 2 - Not Blocking | J06 | J06 | Air renewal ventilation system: Setting Configurations | BH;FH;OO | 24 - Ventilate the ship | HCT |  | To ventilate the ship in the different configurations: | Local / Remote (monitoring from CSP) | Partial
SBR4 | 1006 | S02 DMZ0009 | 1 - Validated by ICN | J06 | J06 | Common suction circuit Leak test | DA;DM;DN | 10 - Control ship weight | PTRH |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Local / Remote (DA, DM). Local (DN). | Nominal
SBR4 | 1007 | S02 DMZ0010 | 1 - Validated by ICN | J06 | J06 | DM00001 and DM00002 centrifugal pumps degassing circuits in fwd auxiliary room Leak test | DA;DM;DN | 10 - Control ship weight | PTRH |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Local / Remote (DA, DM). Local (DN). | Nominal
SBR4 | 1008 | S02 DM00230 | 1 - Validated by ICN | J06 | J06 | Complete regulating tank Leak test | DA;DM;DN | 10 - Control ship weight | PTRH |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Local / Remote (DA, DM). Local (DN). | Nominal
SBR4 | 1009 | S02 DAZ0002 | 1 - Validated by ICN | J06 | J06 | Central draining tank DA00037 with vent and overflow circuit Leak test | DA;DM;DN | 10 - Control ship weight | PTRH |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Local / Remote (DA, DM). Local (DN). | Nominal
SBR4 | 1010 | S02 DAZ0004 | 1 - Validated by ICN | J06 | J06 | Aft auxiliary compartment draining circuit Leak test | DA;DM;DN | 10 - Control ship weight | PTRH |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Local / Remote (DA, DM). Local (DN). | Nominal
SBR4 | 1012 | S02 DAZ0007 | 1 - Validated by ICN | J06 | J06 | Torpedo bilge draining circuit and forward bilge pump discharge circuit Leak test | DA;DM;DN | 10 - Control ship weight | PTRH |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Mode: Local / Remote (DA, DM). Local (DN) | Nominal
SBR4 | 1014 | S02 DAZ0009 | 1 - Validated by ICN | J06 | J06 | Central bilge-draining tank DA00037 and snorting draining tank BH00007 draining circuit Leak test | DA;DM;DN | 10 - Control ship weight | PTRH |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Mode: Local / Remote (DA, DM). Local (DN) | Nominal
SBR4 | 1022 | F02 DMZ0001 | 1 - Validated by ICN | J06 | J06 | Check of the valves mounting direction and operation | DA;DM;DN | 10 - Control ship weight | AIS |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Mode: Local / Remote (DA, DM). Local (DN) | Nominal
SBR4 | 1025 | F02 DNZ0003 | 1 - Validated by ICN | J06 | J06 | Check of the operation of trim clinometers DN00151, DN00251, DN00253 and DN00258 | DA;DM;DN | 10 - Control ship weight | AIS |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Mode: Local / Remote (DA, DM). Local (DN) | Nominal
SBR4 | 1026 | F02 DNZ0004 | 1 - Validated by ICN | J06 | J06 | Check of the operation of list clinometers DN00152, DN00252, DN00256 and DN00259 | DA;DM;DN | 10 - Control ship weight | AIS |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Mode: Local / Remote (DA, DM). Local (DN) | Nominal
SBR4 | 1027 | Test DM2C partial (Except elementary test n°8) | 3 - Blocking | J06 | J06 | Setting to work of the weight compensating system | DA;DM;DN | 10 - Control ship weight | STW |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Mode: Local / Remote (DA, DM). Local (DN) | Nominal
SBR4 | 1029 | Test DA1C partial Elementary test 4, 5, 6, 7 and 8. | 1 - Validated by ICN | J06 | J06 | Setting to work of bilge draining system | DA;DM;DN | 10 - Control ship weight | STW |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Mode: Local / Remote (DA, DM). Local (DN) | Nominal
SBR4 | 1030 | Test DA2C | 5 - Waiting Proof | J06 | J06 | Functional test of bilge draining system at harbor | DA;DM;DN | 10 - Control ship weight | HCT |  | To control the ship weight and drain the bilge of the ship. To control the ship platform attitudes (List). | Mode: Local / Remote (DA, DM). Local (DN) | Nominal
SBR4 | 1102 | B05 AC32087 | 3 - Blocking | J08 (J06) | J06 | Penetration outfitting according to “Pressure Hull integrity” plan AC32087 | AC;HL;UE | 36 - Pressure hull integrity | B05 |  | Pressure hull integrity by compliance of all penetration outfitting inspections. | Local |  | AC32087 | AC32087 ; AC42087 ; HL22101D ; UE ; HL42087 | under water line | 21
SBR4 | 1110 | S02 EQZ0012 | 1 - Validated by ICN | J06 | J06 | Leak test of Buoy release air circuit | EQ | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity (Ram rod control hydraulic circuit and buoy release air circuit). | Local
SBR4 | 1193 | Shipyard report | 1 - Validated by ICN | J06 | J06 | Presence of the limber holes on the top of all main ballast tanks, in every diesel oil tanks (EG) in every regulating/compensating tanks (DM), in every freshwater tanks (EJ), and in weapon compensating and operating tanks (KT) | Several | 99 - Several | Shipyard prerequisites |  | To perform the setting afloat in safe conditions in compliance with the weight and stability requirements | local | Nominal
SBR4 | 1576 | S02 BHZ0004 | 1 - Validated by ICN | J06 | J06 | Leak test. Circuits subjected to submergence pressure. | BD;BH;BM;BQ;DN;OO | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity | Local | Available for sailing / Unavailable for sailing
SBR4 | 1618 | S02 HEZ0004 | 1 - Validated by ICN | J06 | J06 | Leak test of flares launching basket circuits HE00100 | HE | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1619 | S02 HEZ0005 | 1 - Validated by ICN | J06 | J06 | Leak test of flares launching basket circuits HE00200 | HE | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1620 | S02 HEZ0006 | 1 - Validated by ICN | J06 | J06 | Leak test of flares launching basket circuits HE00300 | HE | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1621 | S02 HEZ0007 | 1 - Validated by ICN | J06 | J06 | Leak test of flares launching basket circuits HE00400 | HE | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1723 | S02 FQZ0003 | 5 - Waiting Proof | J06 | J06 | Circuits subjected to submergence pressure. Leak test | FQ | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1724 | S02 BHZ0001 | 1 - Validated by ICN | J06 | J06 | Leak test. Circuits subjected to submergence pressure. | BH | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity | Local | Available for sailing / Unavailable for sailing
SBR4 | 1726 | S02 BHZ0003 | 1 - Validated by ICN | J06 | J06 | Leak test. Circuits subjected to submergence pressure. | BH | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity | Local | Available for sailing / Unavailable for sailing
SBR4 | 1731 | S02 ERZ0001 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. | ER | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1732 | S02 ERZ0002 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. | ER | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1733 | S02 EXZ0001 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak pressure tests of the highpressure feed section for the towing hook, and clinch hook. | EX | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1734 | S02 EXZ0004 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP Leak test of forward hydraulic circuit | EX | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1735 | S02 EXZ0006 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. HP Leak test of forward hydraulic circuit | EX | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1736 | S02 KTZ0015 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1737 | S02 KTZ0016 | 3 - Blocking | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1738 | S02 KTZ0017 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1739 | S02 KTZ0018 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1740 | S02 KTZ0019 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1741 | S02 KTZ0020 | 4 - Under Analysis | J06 | J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1744 | S02 KTZ0035 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1745 | S02 KTZ0036 | 3 - Blocking | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1746 | S02 KTZ0037 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1747 | S02 KTZ0038 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1748 | S02 KTZ0039 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1749 | S02 KTZ0040 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1750 | S02 KTZ0041 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1751 | S02 KTZ0042 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1752 | S02 KTZ0043 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1753 | S02 KTZ0044 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1754 | S02 KTZ0045 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1755 | S02 KTZ0046 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | KT | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1758 | S02 RMZ2008 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of hydraulic circuit of MultiCom Mast | RM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1759 | S02 RMZ2010 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of hydraulic circuit of MultiCom Mast | RM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1760 | S02 RMZ2011 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of hydraulic circuit of MultiCom Mast | RM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1761 | S02 RMZ2014 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of compress gas circuit of MultiCom Mast | RM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1762 | S02 RMZ2016 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of compress gas circuit of ESM Mast | RM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1763 | S02 RMZ2017 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of compress gas circuit of Radar Mast | RM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1764 | S02 ULZ0001 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test | UL | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 1765 | S02 ULZ0002 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test of air accumulator inflation circuit | UL | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 3005 | G07 inspection | 1 - Validated by ICN | J06 | J06 | Check of the good positioning of the draught marks | Several | 99 - Several | Shipyard prerequisites |  | To perform the setting afloat in safe conditions in compliance with the weight and stability requirements | local | Nominal.
SBR4 | 3095 | Shipyard certificate - Greasing - J06 | 5 - Waiting Proof | J06 | J06 | Greasing circuits filled with grease | Several | 99 - Several | Shipyard prerequisites |  | Control & Monitoring
SBR4 | 3096 | Test SHIP14C partial Elementary n°2 table n°4 | 5 - Waiting Proof | J06 | J06 | Safety equipment availability, good condition and use-by date validity – J01/J03 to J06 scope. | Several | 99 - Several | Shipyard prerequisites |  | Guaranty availability, good condition and use-by date validity of safety equipment and safety onboard dotation | Not applicable. | Nominal
SBR4 | 3097 | Shipyard report - Safety onboard dotation - J06 | 1 - Validated by ICN | J06 | J06 | Safety onboard dotation equipment availability, good condition and useby date validity – J01/J03 to J06 scope. | Several | 99 - Several | Shipyard prerequisites |  | Guaranty availability, good condition and use-by date validity of safety equipment and safety onboard dotation | Not applicable. | Nominal
SBR4 | 3098 | On-board safety inspection - J06 | 5 - Waiting Proof | J06 | J06 | (J06 On-board safety inspection- check list) | Several | 99 - Several | Shipyard prerequisites |  | Check the ship condition in terms of safety and the organization implemented by the shipyard | Not applicable. | Nominal
SBR4 | 3099 | Shipyard report (SOD) - J06 | 5 - Waiting Proof | J06 | J06 | Check of the presence and correct configuration of the movement restrictions according to Submarine Operating Documentation (SOD) – Alongside situation. To be performed for every setting afloat | Several | 99 - Several | Shipyard prerequisites |  | Presence and correct configuration of the movement restrictions | local | Nominal.
SBR4 | 3100 | Shipyard report - Tables 1 to 9 from SMB-210913 and Inspections outcome - J06 | 5 - Waiting Proof | J06 | J06 | Preparation phase for undocking - Loading configuration of the ship - Inspections (marking of a measurement reference on the main ballast tanks grids, bilges dry and cleanliness status) | Several | 99 - Several | Shipyard prerequisites |  | Submarine in compliance with the weight and stability requirements for undocking | - | -
SBR4 | 3101 | Stability note | 1 - Validated by ICN | J06 | J06 | Weight and stability calculations for undocking | Several | 99 - Several | Shipyard prerequisites | To be provided by Naval Group Design Authority based on the loading configuration of ship provided by ICN above. | Submarine in compliance with the weight and stability requirements for undocking | - | -
SBR4 | 3102 | Shipyard report Tables 10 to 12 from SMB-210913 | 2 - Not Blocking | J06 | J06 | Weight and stability measurement after undocking | Several | 99 - Several | Shipyard prerequisites | To be performed just after undocking and prior to modify the submarine loading status (e.g. disembarking of the crew) | Submarine in compliance with the weight and stability requirements for undocking | - | -
SBR4 | 3103 | Shipyard report | 5 - Waiting Proof | J06 | J06 | Make sure that protection covers for AC and DC networks shore connection deck plugs are available Th | Several | 99 - Several | Shipyard prerequisites |  | Availability of Protections covers for AC and DC networks shore connection deck plugs | Local | Nominal
SBR4 | 3105 | S02 BMZ0005 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak tests of the cooling air blowing circuit | BD;BM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 3106 | S02 BMZ0006 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak tests of the cooling air blowing circuit | BD;BM | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 3107 | S02 FPZ0001 | 1 - Validated by ICN | J06 | J06 | Circuits subjected to submergence pressure. Leak test | FP | 01 - Sea water circuit integrity | PTRH |  | To know the status of the circuits submitted to submergence pressure integrity. | Local | Available for sailing / Unavailable for sailing
SBR4 | 3109 | Test SHIP14C.2 partial Elementary n°2 Table 4 - J06 | 5 - Waiting Proof | J06 | J06 | Fresh water tank Nb 2 water level over low level (Supplying water mist) | EF;EJ;OO | 14 - Fight the fire | PTRH |  | Firefighting in electrical switchboards and battery rooms. Firefighting in diesel compartment | Local | Partial
SBR4 | 3111 | Shipyard Certificate - Presence mask | 5 - Waiting Proof | J06 | J06 | Presence of 1 mask per person on board during the setting afloat and presence of 2 Air breathing masks with portable bottle | EZ | 15 - Breathing air network | Shipyard prerequisites |  | To have breathing air network | local, monitoring remote (from DSP) | Nominal
SBR4 | 3113 | Shipyard Certificate - Non-regression - J06 | 5 - Waiting Proof | J06 | J06 | Non-regression of J01/J02/J03/J04 vital function | Several | 99 - Several | Shipyard prerequisites |  | Non-regression of J01/J02/J03/J04 vital function
SBR4 | 3277 | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | J06+ | J06 | The weather conditions must be checked before lhe operating and lhe positioning at quay. | Several | 99 - Several | Shipyard prerequisites |  | The weather conditions must be checked before lhe operating and lhe positioning at quay.
SBR4 | 3278 | Shipyard Certificate - RIC reporting that manual lubrication was performed and listing the items | 5 - Waiting Proof | J06+ | J06 | Greasing of all the mobile items including some pipes circuits such as external doors (WLTs), hatches, masts, steering gear (bushes), ... to be implemented. | Several | 99 - Several | Shipyard prerequisites |  | Greasing of all the mobile items including some pipes circuits such as external doors (WLTs), hatche
SBR4 | 3279 | Shipyard Certificate - RIC informing that all the equipment necessary for the movement of people in | 5 - Waiting Proof | J06+ | J06 | lnspection of the casing panels after remounting with EX safety rai ls trolley test afterwards. | Several | 99 - Several | Shipyard prerequisites |  | lnspection of the casing panels after remounting with EX safety rai ls trolley test afterwards.
SBR4 | 3280 | Shipyard Certificate - RIC with the list of keys and where they are stored | 5 - Waiting Proof | J06+ | J06 | Set of lockers, chains, keys to be prepared for internal opening locking. Keys to be preserved onboard with lhe team in charge. | Several | 99 - Several | Shipyard prerequisites |  | Set of lockers, chains, keys to be prepared for internal opening locking. Keys to be preserved onboa
SBR4 | 3281 | Shipyard Certificate - RIC with the list of external areas inspected by BN | 5 - Waiting Proof | J06+ | J06 | All external areas not accessible once the ship will be afloat or under the water line must be accepted by BN and set to idle situation (ballasts, forward framework, ... ) | Several | 99 - Several | Shipyard prerequisites |  | All external areas not accessible once the ship will be afloat or under the water line must be accep
SBR4 | 3282 | Shipyard Certificate - RIC equip, cables and piping were fixed and protected | 5 - Waiting Proof | J06+ | J06 | ln addition with hull integrity rounds checking and monitoring, rounds to secure/fix or protect externai equipmenl to be organized before lhe mounting of lhe casing paneis. | Several | 99 - Several | Shipyard prerequisites |  | ln addition with hull integrity rounds checking and monitoring, rounds to secure/fix or protect exte
SBR4 | 3284 | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | J06+ | J06 | Access onboard: Nominal access onboard through the access trunk only. AII the other access being closed after vacuum test prior during launching, hauling and mooring. | Several | 99 - Several | Shipyard prerequisites |  | Access onboard: Nominal access onboard through the access trunk only. AII the other access being clo
SBR4 | 3285 | Shipyard Certificate - Evidence reference - RIC-xxxx | 5 - Waiting Proof | J06+ | J06 | BE - Portable torches available onboard in case of loss of power supply. | Several | 99 - Several | Shipyard prerequisites |  | BE - Portable torches available onboard in case of loss of power supply
SBR4 | 3286 | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | J06+ | J06 | HG - Communication between the team onboard. the quay and the tug boats (talkie-walkies). | Several | 99 - Several | Shipyard prerequisites |  | HG - Communication between the team onboard. the quay and the tug boats (talkie-walkies).
SBR4 | 3287 | Shipyard Certificate - STW EZ | 4 - Under Analysis | J06+ | J06 | EZ - Breathing equipment (air breathing masks with portable bottle) for teams inside the ship out of lhe firefighter equipment to be evaluated. | Several | 99 - Several | Shipyard prerequisites |  | EZ - Breathing equipment (air breathing masks with portable bottle) for teams inside the ship out of
SBR4 | 3288 | Shipyard Certificate - STW EF | 5 - Waiting Proof | J06+ | J06 | EF - Detection onboard and firefighting (extinguishers, equipped fire fighter, breathing equipment) | Several | 99 - Several | Shipyard prerequisites |  | EF - Detection onboard and firefighting (extinguishers, equipped fire fighter, breathing equipment)
SBR4 | 3289 | Shipyard Certificate - Evidence reference - RIC-xxxx | 5 - Waiting Proof | J06+ | J06 | DA - Portable pumps to drain the bilges in case of leakage (forward and aft areas). | Several | 99 - Several | Shipyard prerequisites |  | DA - Portable pumps to drain the bilges in case of leakage (forward and aft areas).
SBR4 | 3290 | Shipyard Certificate - STW BT | 5 - Waiting Proof | J06+ | J06 | BT - Availability of partial subsystem BT power supply at least in 8350, auxiliary compartments (to supply portable pumps for instance). | Several | 99 - Several | Shipyard prerequisites |  | BT - Availability of partial subsystem BT power supply at least in 8350, auxiliary compartments (to
SBR4 | 3291 | Shipyard Certificate - Evidence reference - RIC-xxxx | 5 - Waiting Proof | J06+ | J06 | Set of tools onboard in case of leakage as a first intervention (mechanical, electricity, piping). | Several | 99 - Several | Shipyard prerequisites |  | Set of tools onboard in case of leakage as a first intervention (mechanical, electricity, piping).
SBR4 | 3292 | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | J06+ | J06 | Safety and configuration of the deck (lifeline, "filiéres (spinneret)", sail's handrail) | Several | 99 - Several | Shipyard prerequisites |  | Safety and configuration of the deck (lifeline, "filiéres (spinneret)", sail's handrail)
SBR4 | 3293 | Shipyard Certificate - RIC with the EPIs that will be used | 5 - Waiting Proof | J06+ | J06 | Set of individual safety means (including life jackets, safety harness). | Several | 99 - Several | Shipyard prerequisites |  | Set of individual safety means (including life jackets, safety harness).
SBR4 | 3294 | Shipyard Certificate - Evidence reference - RIC-xxxx | 5 - Waiting Proof | J06+ | J06 | Power supply configuration: battery to be set up. | Several | 99 - Several | Shipyard prerequisites |  | Power supply configuration: battery to be set up.
SBR4 | 3295 | Shipyard Certificate - Training report Checklist for controls and records - LV | 5 - Waiting Proof | J06+ | J06 | Safety drills to be organized by ICN as per the safety measures list. | Several | 99 - Several | Shipyard prerequisites |  | Safety drills to be organized by ICN as per the safety measures list
SBR4 | 3298 | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | J06+ | J06 | ICN procedures to be prepared: Transfer Main Hall to Ship lift, Undocking (in annex, the procedure will describe in ali the configurations how the ship can be undocked on decision of the dock master), Hauling and Mooring. | Several | 99 - Several | Shipyard prerequisites |  | ICN procedures to be prepared: Transfer Main Hall to Ship lift, Undocking (in annex, the procedure w
SBR4 | 3299 | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | J06+ | J06 | ICN organization and responsibilities for the transfer and undocking, hauling, and mooring phases (teams, distribution onboard, who do what, safety cycling, registers, communication between onboard and quay, tug boats, divers ... ). | Several | 99 - Several | Shipyard prerequisites |  | ICN organization and responsibilities for the transfer and undocking, hauling, and mooring phases (t
SBR4 | 3306 | Shipyard Certificate - Temporary Instructions - J06 | 5 - Waiting Proof | J06 | J06 | Temporary instructions must be issued by ICN before every seaout | Several | 99 - Several | Shipyard prerequisites |  | Temporary instructions