## Merged Analysis
J06 Items: Analysis, Status & Responsibility
SBR4 · GTO List of Items · gerado em 28/07/2026 08:25 · 218 itens (ActualJx = J06) · 59 pendencias abertas | [6 empty] | Última atualização: 28/07/2026 08:25
Item | Context | OriginalJx | ActualJx | Category | Description | Certificate / Evidence | Status Anterior | Status Atual | Analysis (EN) | Responsible | Analysis (PT)
2 | SBR4 | J01 & J03 | J06 | General J06 | Broadcasting safety alarms to all rooms of the ship. | Test HP2C | 5 - Waiting Proof | 4 - Under Analysis | Check the RIC to be done. | Ship Manager | Verificar o RIC a ser emitido.
39 | SBR4 | J01 & J03 | J06 | General J06 | Aft battery room: BB00060 - Leak test: Fitted room (0.2bar). | S02 BBZ0006 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
49 | SBR4 | J01 & J03 | J06 | General J06 | Forward battery room: BB00070: Leak test: Fitted room (0.2bar). | S02 BBZ0007 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
133 | SBR4 | J01 & J03 | J06 | General J06 | Functional test | Test BF1C | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
207 | SBR4 | J02 & J04 | J06 | General J06 | EV Water cooling circuit (battery). Leak test. | S02 EVZ0002 | 2 - Not Blocking | 2 - Not Blocking | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
208 | SBR4 | J02 & J04 | J06 | General J06 | BB Water cooling circuit. Distilled water circuit. Leak test: circuit to batteries. | S02 BBZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
209 | SBR4 | J02 & J04 | J06 | General J06 | BB Water cooling circuit. Leak test: aft battery. | S02 BBZ0004 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
211 | SBR4 | J02 & J04 | J06 | General J06 | Electrolyte agitation circuit. Leak test. | S02 BBZ0008 | 3 - Blocking | 4 - Under Analysis To Not Blocking | Test folder indicates pendencies from NG. | NG (Naval Group) | A pasta de testes indica pendências do NG.
214 | SBR4 | J02 & J04 | J06 | General J06 | Electrolyte agitation system. | Test BB1C partial Elementary nº1 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
243 | SBR4 | J02 & J04 | J06 | General J06 | BB Water cooling circuit. Leak test: forward battery. | S02 BBZ0005 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
326 | SBR4 | J05 (J06Cer) | J06 | General J06 | Firefighting electric pump Leak pressure test of the water mist feed circuit to the diesel diffusers | S02 EFZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
405 | SBR4 | J06 | J06 | General J06 | Water tightness mastered status according to procedure of the hull watertightness management for submarine [R3], including ¿ Onboard inspection part: The Hull Watertightness Manager must be present during the inspection with the BIC report to cross check the situation with the Watch and Operation Team. Cross check requirements: - Actual Circuit status is consistent with circuit status in the BIC report (especially absence of not declared works); - Counterfoil booklet status is consistent with the actual circuit status; - In case of specific provisions (including restriction devices) defined by the BIC report, they are implemented on board. (description and visual check to be reported). ¿ Identification of works from last safety milestones and traceability folder. | Shipyard report (BIC report) - J06 | 5 - Waiting Proof | 5 - Waiting Proof | Report to be delivered after vacuum test. | GTO | Relatório a ser entregue após o teste de vácuo.
406 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure Leak test | S02 BMZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
407 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure Leak test | S02 BMZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
408 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure Leak test | S02 BMZ0003 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
409 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure Leak test | S02 BMZ0004 | 5 - Waiting Proof | 4 - Under Analysis | Test folder with comissioning to be done. | Commissioning | Pasta de testes a ser concluída pelo comissionamento.
411 | SBR4 | J06 | J06 | General J06 | Leak test. Circuits subjected to submergence Circuits subjected to submergence pressure. | S02 DMZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
412 | SBR4 | J06 | J06 | General J06 | Leak test. Circuits subjected to submergence Circuits subjected to submergence pressure. | S02 DMZ0002 | 5 - Waiting Proof | 1 - Validated by ICN | Test folder with production team to be delivered. | Production | Pasta de testes a ser entregue pela equipe de produção.
415 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test | S02 DNZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
416 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test | S02 DNZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
417 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test | S02 DNZ0003 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
426 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Entire EM circuit | S02 EMZ0003 | 5 - Waiting Proof | 1 - Validated by ICN | Test done, pending the evidence only. | Quality | Teste realizado, pendente somente da evidência.
432 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Entire EN circuit | S02 ENZ0003 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
434 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | S02 KTZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
435 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | S02 KTZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
436 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | S02 KTZ0003 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
437 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | S02 KTZ0004 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
438 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | S02 KTZ0005 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
439 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the filling/draining circuit of tube | S02 KTZ0006 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
442 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the draining circuit of tube | S02 KTZ0009 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
443 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the draining circuit of tube | S02 KTZ0010 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
445 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the draining circuit of tube | S02 KTZ0012 | 3 - Blocking | 1 - Validated by ICN | Test done, pending the evidence only. | Quality | Teste realizado, pendente somente da evidência.
446 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the circuit upstream of the equalizing valves | S02 KTZ0013 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
447 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the circuit upstream of the equalizing valves | S02 KTZ0014 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
451 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test | S02 MBZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
461 | SBR4 | J06 | J06 | General J06 | Setting to work of bilge draining system Check the water volumes of draining tanks Table 1 and 2 | Test DA1C Elementary test 1 Local mode and DSP | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
462 | SBR4 | J06 | J06 | General J06 | Setting to work of bilge draining system Check the volume of the bilges Table 3 | Test DA1C Elementary test 2 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
463 | SBR4 | J06 | J06 | General J06 | Setting to work of bilge draining system Low, Incident and defect level for all tanks and bilges Table 4 and 5 | Test DA1C Elementary test 3 at least DSP | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
487 | SBR4 | J06 | J06 | General J06 | Leak test. Circuits subjected to submergence pressure. | S02 DBZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
494 | SBR4 | J06 | J06 | General J06 | Leak test. Circuits subjected to submergence pressure. | S02 DB00601 | 3 - Blocking | 1 - Validated by ICN | Test to be redone by NCR 1236 | Ship Manager | Teste a ser refeito pela NCR 1236.
526 | SBR4 | J06 | J06 | General J06 | Functional test of vent valves in local control checking of the vent valves and the manual distributor. | Test DB1C partial Elementary n°1 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
528 | SBR4 | J06 | J06 | General J06 | Drain valves & circuits tightness test over 24 hours Important: Test to be done just after the setting afloat. If not satisfactory, the ship shall be brought back in drydock. | Test DB2C | 2 - Not Blocking | 2 - Not Blocking | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
560 | SBR4 | J06 | J06 | General J06 | Communication between quayside and the submarine | Shipyard certificate Communication between quayside and the submarine - J06 | 4 - Under Analysis | 4 - Under Analysis |  | NG (Naval Group)
564 | SBR4 | J06 | J06 | General J06 | Test for the correct functioning of the emergency lighting network | Test BE1C partial Elementary n°1 | 4 - Under Analysis To Not Blocking | 4 - Under Analysis To Not Blocking |  | NG (Naval Group)
566 | SBR4 | J06 | J06 | General J06 | Good functioning of the fire detection. | Trial EF 6 At least local and DSP | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
570 | SBR4 | J06 | J06 | General J06 | Running test - Water mist system – Local and remote control and monitoring | Test EF2C partial Elementary n°1 Table 1 & 2 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
571 | SBR4 | J06 | J06 | General J06 | Functional trial of fixed firefighting sub system. | Trial EF2 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
575 | SBR4 | J06 | J06 | General J06 | Gas analysers (O2, CO, CO2) Functional tests. | Test FR2C partial Elementary n°1 table 2 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
585 | SBR4 | J06 | J06 | General J06 | Switchboard safety. Assembly, connecting and grounding. | E01 BS02507 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
605 | SBR4 | J06 | J06 | General J06 | Air renewal ventilation system : Configurations ventilation charts in battery rooms | FH2C | 4 - Under Analysis To Not Blocking | 2 - Not Blocking | Status closed - no pending action. | NG (Naval Group) | Status encerrado - sem acao pendente.
607 | SBR4 | J06 | J06 | General J06 | Gas analysers (H2). Functional tests. | Test FR2C partial Elementary n°1 table 2 (Local and remote mode) | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
609 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30001 | B05 AC30001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
610 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30005 | B05 AC30005 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
611 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30010 | B05 AC30010 | 3 - Blocking | 3 - Blocking | Hatch to be mounted. | Production | Escotilha a ser montada.
612 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30020 | B05 AC30020 | 2 - Not Blocking | 2 - Not Blocking | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
613 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30030 | B05 AC30030 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
614 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30040 | B05 AC30040 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
616 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30051 | B05 AC30051 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
618 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30053 | B05 AC30053 | 3 - Blocking | 3 - Blocking | Waiting evidences | Quality | Aguardando evidências.
619 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30060 | B05 AC30060 | 3 - Blocking | 3 - Blocking | Waiting the last inspetions | Quality | Aguardando as últimas inspeções.
620 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30070 | B05 AC30070 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
621 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30071 | B05 AC30071 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
622 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30080 | B05 AC30080 | 3 - Blocking | 3 - Blocking | Mounting to finished. | Production | Montagem a ser finalizada.
623 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30090 | B05 AC30090 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
624 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30101 | B05 AC30101 | 3 - Blocking | 3 - Blocking | Tests folder with quality team | Quality | Pasta de testes com a equipe da qualidade.
625 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30102 | B05 AC30102 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
626 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30103 | B05 AC30103 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
627 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30104 | B05 AC30104 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
628 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30105 | B05 AC30105 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
629 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC30106 | B05 AC30106 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
636 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC31014 - Lubricating oil supply EL00006 | B05 AC31014 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
638 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC31016 | B05 AC31016 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
645 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32002 - Diesel supply EG00101 (diesel) | B05 AC32002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
646 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32003 - Diesel supply EQ00411 (água) | B05 AC32003 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
647 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32004 | B05 AC32004 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Waiting NCR 733 to close only. | NG (Naval Group) | Aguardando somente o fechamento da NCR 733.
648 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32005 | B05 AC32005 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Waiting NCR 733 to close only. | NG (Naval Group) | Aguardando somente o fechamento da NCR 733.
649 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32006 | B05 AC32006 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Waiting NCR 733 to close only. | NG (Naval Group) | Aguardando somente o fechamento da NCR 733.
650 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32007 | B05 AC32007 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Waiting NCR 733 to close only. | NG (Naval Group) | Aguardando somente o fechamento da NCR 733.
651 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32008 | B05 AC32008 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Waiting NCR 733 to close only. | NG (Naval Group) | Aguardando somente o fechamento da NCR 733.
652 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32009 | B05 AC32009 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Waiting NCR 733 to close only. | NG (Naval Group) | Aguardando somente o fechamento da NCR 733.
653 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32010 | B05 AC32010 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
654 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32011 | B05 AC32011 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Waiting NCR 733 to close only. | NG (Naval Group) | Aguardando somente o fechamento da NCR 733.
655 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32012 | B05 AC32012 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
657 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32014 | B05 AC32014 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
658 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32015 | B05 AC32015 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Waiting NCR 733 to close only. | NG (Naval Group) | Aguardando somente o fechamento da NCR 733.
660 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32023 | B05 AC32023 | 3 - Blocking | 3 - Blocking | Waiting evidences | Quality | Aguardando evidências.
661 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32024 | B05 AC32024 | 3 - Blocking | 3 - Blocking | Waiting evidences | Quality | Aguardando evidências.
667 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32030 | B05 AC32030 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
673 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32038 - Water supply EQ00412 | B05 AC32038 | 3 - Blocking | 3 - Blocking | Last evidence to de done bay comissioning the moment before vacuum test. | Commissioning | Última evidência a ser feita pelo comissionamento no momento anterior ao teste de vácuo.
676 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32050 - Sanitary tank FQ00804 | B05 AC32050 | 1 - Validated by ICN | 3 - Blocking
704 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33000 | B05 AC33000 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
705 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33001 | B05 AC33001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
706 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33002 | B05 AC33002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
708 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33004 | B05 AC33004 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
711 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33009 | B05 AC33009 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
714 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33012 | B05 AC33012 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
718 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33018 | B05 AC33018 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Jus SIGN pending | Commissioning | Pendente apenas a assinatura (SIGN).
719 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33019 | B05 AC33019 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
725 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33028 | B05 AC33028 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
729 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33043 | B05 AC33043 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | B05 paper | GTO | Documento B05.
730 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33050 | B05 AC33050 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
732 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33052 | B05 AC33052 | 2 - Not Blocking | 2 - Not Blocking | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
733 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33053 | B05 AC33053 | 3 - Blocking | 3 - Blocking | Waiting evidences | Quality | Aguardando evidências.
736 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33056 | B05 AC33056 | 7 - Missing Vacuum Test or Sign | 7 - Missing Vacuum Test or Sign | Waiting Vacuum test only | Ship Manager | Aguardando somente o teste de vácuo.
743 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC33064 | B05 AC33064 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
751 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC34024 | B05 AC34024 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
752 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC34025 | B05 AC34025 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
756 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC34030 | B05 AC34030 | 3 - Blocking | 3 - Blocking | Waiting evidences | Quality | Aguardando evidências.
764 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC34040 | B05 AC34040 | 4 - Under Analysis To Not Blocking | 2 - Not Blocking | Status closed - no pending action. | NG (Naval Group) | Status encerrado - sem acao pendente.
765 | SBR4 | J06 | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC34041 | B05 AC34041 | 4 - Under Analysis To Not Blocking | 2 - Not Blocking | Status closed - no pending action. | NG (Naval Group) | Status encerrado - sem acao pendente.
777 | SBR4 | J06 | J06 | General J06 | Hatches Functional test | Test AG1C | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
779 | SBR4 | J06 | J06 | General J06 | Safety device Sewage tank FQ | Test FQ1C partial Table 2 | 5 - Waiting Proof | 1 - Validated by ICN | Check the date for the test | Ship Manager | Verificar a data do teste.
780 | SBR4 | J06 | J06 | General J06 | Safety device Submerged signal ejector UL | Test UL0C partial Elementary 5 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
781 | SBR4 | J06 | J06 | General J06 | Safety device Torpedo tubes KT | Test KT4C | 5 - Waiting Proof | 1 - Validated by ICN | Check the date for the test | Ship Manager | Verificar a data do teste.
782 | SBR4 | J06 | J06 | General J06 | Water tightness monitoring Hull pressure integrity status according to the Procedure of the hull watertightness management for submarine SMB-360103 [R4] including 1- Onboard inspection part: The Hull Watertightness Manager must be present during the inspection with the BOC report to cross check the situation with the Watch and Operation Team. Cross check requirements: - Actual Circuit status is consistent with penetration status in the BOC report (especially absence of not declared works); - Counterfoil booklet status is consistent with the actual penetration status; - In case of specific provisions (including restriction devices) defined by the BOC report, they are implemented on board. (description and visual check to be eported). 2- Identification of works from last safety milestones and traceability folder. | Shipyard report (BOC Report) - J06 | 5 - Waiting Proof | 5 - Waiting Proof | Report to be delivered after vacuum test. | GTO | Relatório a ser entregue após o teste de vácuo.
783 | SBR4 | J06 | J06 | General J06 | Safety device Garbage unit FP Safety checks are the following ones: 1- Impossibility to open the ball valve when the upper hatch is unlocked. 2- Impossibility to unlock the upper hatch when the ball valve is not completely shut. 3- Impossibility to unlock the upper hatch when the vent valve is shut | Shipyard report (Garbage unit FP) - J06 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
784 | SBR4 | J06 | J06 | General J06 | General depression test on board - To be performed before every setting afloat | SHIP2C (General depression test on board) - J06 | 5 - Waiting Proof | 5 - Waiting Proof | Evidence to be done after vacuum test | Ship Manager | Evidência a ser feita após o teste de vácuo.
785 | SBR4 | J06 | J06 | General J06 | Document to be produce by ICN in conformity with SOI, This includes specifically SOD_M2_CH_1-14 “Refloating” | Apply Submarine Operating Instructions (SOI) - J06 | 5 - Waiting Proof | 1 - Validated by ICN | Just a general document from ICN to be sent. | Ship Manager | Apenas um documento geral da ICN a ser enviado.
786 | SBR4 | J06 | J06 | General J06 | Monitoring of the following alarms: Availability of the ventilation (loss of flow rate and pressure), Position Open/Closed of the battery ventilation valves, Fire detection, Hydrogen detection, Flooding detection. | Main Safety Office is manned 24x7 by qualified personnel - J06 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
809 | SBR4 | J06 | J06 | General J06 | Functional test of the voice-activated telephone network | Test HG1C Elementary n°1 and 2 - J06 | 5 - Waiting Proof | 1 - Validated by ICN | Check the RIC to be done. | Ship Manager | Verificar o RIC a ser emitido.
817 | SBR4 | J06 | J06 | General J06 | Leak pressure tests Aft air production and distribution line | S02 EZZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
818 | SBR4 | J06 | J06 | General J06 | Leak pressure tests Forward air production and distribution line | S02 EZZ0002 | 3 - Blocking | 1 - Validated by ICN | Test done, pending the evidence only. | Quality | Teste realizado, pendente somente da evidência.
820 | SBR4 | J06 | J06 | General J06 | Circuit conservation Forward air production and distribution line | S08 EZZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
822 | SBR4 | J06 | J06 | General J06 | Verification of the free discharge Forward section | S03 EZZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
840 | SBR4 | J06 | J06 | General J06 | Functional tests of air network in harbour | Test EZ2C | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
855 | SBR4 | J06 | J06 | General J06 | Air renewal ventilation system: Setting Configurations | Test FH3C Partial Table 4, 5, 6, 7, 8 and 9 | 4 - Under Analysis To Not Blocking | 2 - Not Blocking | Status closed - no pending action. | NG (Naval Group) | Status encerrado - sem acao pendente.
1006 | SBR4 | J06 | J06 | General J06 | Common suction circuit Leak test | S02 DMZ0009 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1007 | SBR4 | J06 | J06 | General J06 | DM00001 and DM00002 centrifugal pumps degassing circuits in fwd auxiliary room Leak test | S02 DMZ0010 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1008 | SBR4 | J06 | J06 | General J06 | Complete regulating tank Leak test | S02 DM00230 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1009 | SBR4 | J06 | J06 | General J06 | Central draining tank DA00037 with vent and overflow circuit Leak test | S02 DAZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1010 | SBR4 | J06 | J06 | General J06 | Aft auxiliary compartment draining circuit Leak test | S02 DAZ0004 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1012 | SBR4 | J06 | J06 | General J06 | Torpedo bilge draining circuit and forward bilge pump discharge circuit Leak test | S02 DAZ0007 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1014 | SBR4 | J06 | J06 | General J06 | Central bilge-draining tank DA00037 and snorting draining tank BH00007 draining circuit Leak test | S02 DAZ0009 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1022 | SBR4 | J06 | J06 | General J06 | Check of the valves mounting direction and operation | F02 DMZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1025 | SBR4 | J06 | J06 | General J06 | Check of the operation of trim clinometers DN00151, DN00251, DN00253 and DN00258 | F02 DNZ0003 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1026 | SBR4 | J06 | J06 | General J06 | Check of the operation of list clinometers DN00152, DN00252, DN00256 and DN00259 | F02 DNZ0004 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1027 | SBR4 | J06 | J06 | General J06 | Setting to work of the weight compensating system | Test DM2C partial (Except elementary test n°8) | 3 - Blocking | 3 - Blocking | Check the date for the test | Ship Manager | Verificar a data do teste.
1029 | SBR4 | J06 | J06 | General J06 | Setting to work of bilge draining system | Test DA1C partial Elementary test 4, 5, 6, 7 and 8. | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1030 | SBR4 | J06 | J06 | General J06 | Functional test of bilge draining system at harbor | Test DA2C | 5 - Waiting Proof | 5 - Waiting Proof | Check the date for the test | Ship Manager | Verificar a data do teste.
1102 | SBR4 | J08 (J06) | J06 | B05 | Penetration outfitting according to “Pressure Hull integrity” plan AC32087 | B05 AC32087 | 3 - Blocking | 3 - Blocking | Waiting evidences | Quality | Aguardando evidências.
1110 | SBR4 | J06 | J06 | General J06 | Leak test of Buoy release air circuit | S02 EQZ0012 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1193 | SBR4 | J06 | J06 | General J06 | Presence of the limber holes on the top of all main ballast tanks, in every diesel oil tanks (EG) in every regulating/compensating tanks (DM), in every freshwater tanks (EJ), and in weapon compensating and operating tanks (KT) | Shipyard report | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1576 | SBR4 | J06 | J06 | General J06 | Leak test. Circuits subjected to submergence pressure. | S02 BHZ0004 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1618 | SBR4 | J06 | J06 | General J06 | Leak test of flares launching basket circuits HE00100 | S02 HEZ0004 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1619 | SBR4 | J06 | J06 | General J06 | Leak test of flares launching basket circuits HE00200 | S02 HEZ0005 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1620 | SBR4 | J06 | J06 | General J06 | Leak test of flares launching basket circuits HE00300 | S02 HEZ0006 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1621 | SBR4 | J06 | J06 | General J06 | Leak test of flares launching basket circuits HE00400 | S02 HEZ0007 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1723 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test | S02 FQZ0003 | 5 - Waiting Proof | 1 - Validated by ICN | Test done, pending the evidence only. | Quality | Teste realizado, pendente somente da evidência.
1724 | SBR4 | J06 | J06 | General J06 | Leak test. Circuits subjected to submergence pressure. | S02 BHZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1726 | SBR4 | J06 | J06 | General J06 | Leak test. Circuits subjected to submergence pressure. | S02 BHZ0003 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1731 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. | S02 ERZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1732 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. | S02 ERZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1733 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak pressure tests of the highpressure feed section for the towing hook, and clinch hook. | S02 EXZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1734 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP Leak test of forward hydraulic circuit | S02 EXZ0004 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1735 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. HP Leak test of forward hydraulic circuit | S02 EXZ0006 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1736 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | S02 KTZ0015 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1737 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | S02 KTZ0016 | 3 - Blocking | 1 - Validated by ICN | Test done, pending the evidence only. | Quality | Teste realizado, pendente somente da evidência.
1738 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | S02 KTZ0017 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1739 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | S02 KTZ0018 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1740 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | S02 KTZ0019 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1741 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of the blowing air circuits | S02 KTZ0020 | 3 - Blocking | 1 - Validated by ICN | Test done, pending the evidence only. | Quality | Teste realizado, pendente somente da evidência.
1744 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0035 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1745 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0036 | 3 - Blocking | 4 - Under Analysis | Tests folder with quality team | Quality | Pasta de testes com a equipe da qualidade.
1746 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0037 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1747 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0038 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1748 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0039 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1749 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0040 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1750 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0041 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1751 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0042 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1752 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0043 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1753 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0044 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1754 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0045 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1755 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test | S02 KTZ0046 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1758 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of hydraulic circuit of MultiCom Mast | S02 RMZ2008 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1759 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of hydraulic circuit of MultiCom Mast | S02 RMZ2010 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1760 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of hydraulic circuit of MultiCom Mast | S02 RMZ2011 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1761 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of compress gas circuit of MultiCom Mast | S02 RMZ2014 | 5 - Waiting Proof | 1 - Validated by ICN | Evidence received, only BIC to be closed by GTO | GTO | Evidência recebida, faltando somente o BIC ser fechado pela GTO.
1762 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of compress gas circuit of ESM Mast | S02 RMZ2016 | 5 - Waiting Proof | 1 - Validated by ICN | Evidence received, only BIC to be closed by GTO | GTO | Evidência recebida, faltando somente o BIC ser fechado pela GTO.
1763 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of compress gas circuit of Radar Mast | S02 RMZ2017 | 5 - Waiting Proof | 1 - Validated by ICN | Evidence received, only BIC to be closed by GTO | GTO | Evidência recebida, faltando somente o BIC ser fechado pela GTO.
1764 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test | S02 ULZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
1765 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test of air accumulator inflation circuit | S02 ULZ0002 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
3005 | SBR4 | J06 | J06 | General J06 | Check of the good positioning of the draught marks | G07 inspection | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
3095 | SBR4 | J06 | J06 | General J06 | Greasing circuits filled with grease | Shipyard certificate - Greasing - J06 | 5 - Waiting Proof | 5 - Waiting Proof | Just do a RIC informing that the circuits are filled with grease. | Commissioning | Basta emitir um RIC informando que os circuitos estão preenchidos com graxa.
3096 | SBR4 | J06 | J06 | General J06 | Safety equipment availability, good condition and use-by date validity – J01/J03 to J06 scope. | Test SHIP14C partial Elementary n°2 table n°4 | 5 - Waiting Proof | 4 - Under Analysis | Test SHIP14C partial Elementary n°2 table n°4 to be done by comissioning | Commissioning | Teste SHIP14C parcial, Elementar n°2 tabela n°4, a ser feito pelo comissionamento.
3097 | SBR4 | J06 | J06 | General J06 | Safety onboard dotation equipment availability, good condition and useby date validity – J01/J03 to J06 scope. | Shipyard report - Safety onboard dotation - J06 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
3098 | SBR4 | J06 | J06 | General J06 | (J06 On-board safety inspection- check list) | On-board safety inspection - J06 | 5 - Waiting Proof | 5 - Waiting Proof | On-board safety inspection - J06 to be done by ship manager team | Ship Manager | Inspeção de segurança a bordo - J06 a ser feita pela equipe de ship manager.
3099 | SBR4 | J06 | J06 | General J06 | Check of the presence and correct configuration of the movement restrictions according to Submarine Operating Documentation (SOD) – Alongside situation. To be performed for every setting afloat | Shipyard report (SOD) - J06 | 5 - Waiting Proof | 5 - Waiting Proof | RIC to be done by SOP team close to the date for J06. | SOP | RIC a ser feito pela equipe de SOP próximo à data do J06.
3100 | SBR4 | J06 | J06 | General J06 | Preparation phase for undocking - Loading configuration of the ship - Inspections (marking of a measurement reference on the main ballast tanks grids, bilges dry and cleanliness status) | Shipyard report - Tables 1 to 9 from SMB-210913 and Inspections outcome - J06 | 5 - Waiting Proof | 5 - Waiting Proof | Document to be done by ship manager team | Ship Manager | Documento a ser feito pela equipe de ship manager.
3101 | SBR4 | J06 | J06 | General J06 | Weight and stability calculations for undocking | Stability note | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
3102 | SBR4 | J06 | J06 | General J06 | Weight and stability measurement after undocking | Shipyard report Tables 10 to 12 from SMB-210913 | 2 - Not Blocking | 2 - Not Blocking | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
3103 | SBR4 | J06 | J06 | General J06 | Make sure that protection covers for AC and DC networks shore connection deck plugs are available Th | Shipyard report | 5 - Waiting Proof | 5 - Waiting Proof | A RIC to be done by ship manager team. | Ship Manager | Um RIC a ser feito pela equipe de ship manager.
3105 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak tests of the cooling air blowing circuit | S02 BMZ0005 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
3106 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak tests of the cooling air blowing circuit | S02 BMZ0006 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
3107 | SBR4 | J06 | J06 | General J06 | Circuits subjected to submergence pressure. Leak test | S02 FPZ0001 | 1 - Validated by ICN | 1 - Validated by ICN | Status closed — no pending action. | — (Closed – no pending) | Status encerrado — sem ação pendente.
3109 | SBR4 | J06 | J06 | General J06 | Fresh water tank Nb 2 water level over low level (Supplying water mist) | Test SHIP14C.2 partial Elementary n°2 Table 4 - J06 | 5 - Waiting Proof | 4 - Under Analysis | Test SHIP14C.2 partial Elementary n°2 Table 4 - J06 to be done by comissioning | Commissioning | Teste SHIP14C.2 parcial, Elementar n°2 Tabela 4 - J06, a ser feito pelo comissionamento.
3111 | SBR4 | J06 | J06 | General J06 | Presence of 1 mask per person on board during the setting afloat and presence of 2 Air breathing masks with portable bottle | Shipyard Certificate - Presence mask | 5 - Waiting Proof | 5 - Waiting Proof | RIC to be done by PCP responsible for material to be delivered onboard. | PCP | RIC a ser feito pelo PCP responsável pelo material a ser entregue a bordo.
3113 | SBR4 | J06 | J06 | General J06 | Non-regression of J01/J02/J03/J04 vital function | Shipyard Certificate - Non-regression - J06 | 5 - Waiting Proof | 5 - Waiting Proof | Certificate to be issued by GTO team in the final moment for crossing milestone. | GTO | Certificado a ser emitido pela equipe da GTO no momento final para a passagem do marco.
3277 | SBR4 | J06+ | J06 | General J06 | The weather conditions must be checked before lhe operating and lhe positioning at quay. | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | 1 - Validated by ICN | Already validated by ICN. No further evidence required. | — (Closed – no pending) | Já validado pela ICN. Nenhuma evidência adicional necessária.
3278 | SBR4 | J06+ | J06 | General J06 | Greasing of all the mobile items including some pipes circuits such as external doors (WLTs), hatches, masts, steering gear (bushes), ... to be implemented. | Shipyard Certificate - RIC reporting that manual lubrication was performed and listing the items | 5 - Waiting Proof | 5 - Waiting Proof | Commissioning STW ER2C; issue an RIC for the cases done manually. | Commissioning | Comissionamento STW ER2C; emitir um RIC para os casos feitos manualmente.
3279 | SBR4 | J06+ | J06 | General J06 | lnspection of the casing panels after remounting with EX safety rai ls trolley test afterwards. | Shipyard Certificate - RIC informing that all the equipment necessary for the movement of people in | 5 - Waiting Proof | 5 - Waiting Proof | Check whether the safety rail has already been installed and whether the trolley will be used. Issue an RIC. | Ship Manager | Verificar se o safety rail já foi instalado e se o trolley será utilizado. Emitir um RIC.
3280 | SBR4 | J06+ | J06 | General J06 | Set of lockers, chains, keys to be prepared for internal opening locking. Keys to be preserved onboard with lhe team in charge. | Shipyard Certificate - RIC with the list of keys and where they are stored | 5 - Waiting Proof | 5 - Waiting Proof | The Ship Managers team, or those in charge of key custody, can issue the RIC. | Ship Manager | A equipe de Ship Managers, ou os responsáveis pela guarda das chaves, podem emitir o RIC.
3281 | SBR4 | J06+ | J06 | General J06 | All external areas not accessible once the ship will be afloat or under the water line must be accepted by BN and set to idle situation (ballasts, forward framework, ... ) | Shipyard Certificate - RIC with the list of external areas inspected by BN | 5 - Waiting Proof | 5 - Waiting Proof | RIC issued by Production with the submarine on the shiplift. Visual inspection of the external area to ensure there are no pending items in the external area not accessible after floating. Replicate the RIC from SBR3. Check folder. | Production | RIC emitido pela Produção com o submarino no shiplift. Inspeção visual da área externa para garantir que não há pendências na área externa não acessível após a flutuação. Replicar o RIC do SBR3. Verificar a pasta.
3282 | SBR4 | J06+ | J06 | General J06 | ln addition with hull integrity rounds checking and monitoring, rounds to secure/fix or protect externai equipmenl to be organized before lhe mounting of lhe casing paneis. | Shipyard Certificate - RIC equip, cables and piping were fixed and protected | 5 - Waiting Proof | 5 - Waiting Proof | Similar to Item 3281 — same RIC. Replicate the RIC from SBR3. Check folder. | Production | Semelhante ao Item 3281 — mesmo RIC. Replicar o RIC do SBR3. Verificar a pasta.
3284 | SBR4 | J06+ | J06 | General J06 | Access onboard: Nominal access onboard through the access trunk only. AII the other access being closed after vacuum test prior during launching, hauling and mooring. | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | 1 - Validated by ICN | Already validated by ICN. No further evidence required. | — (Closed – no pending) | Já validado pela ICN. Nenhuma evidência adicional necessária.
3285 | SBR4 | J06+ | J06 | General J06 | BE - Portable torches available onboard in case of loss of power supply. | Shipyard Certificate - Evidence reference - RIC-xxxx | 5 - Waiting Proof | 5 - Waiting Proof | Onboard inspection: check all portable torches. | Quality (Onboard Inspection) | Inspeção a bordo: verificar todas as lanternas portáteis.
3286 | SBR4 | J06+ | J06 | General J06 | HG - Communication between the team onboard. the quay and the tug boats (talkie-walkies). | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | 1 - Validated by ICN | Already validated by ICN. No further evidence required. | — (Closed – no pending) | Já validado pela ICN. Nenhuma evidência adicional necessária.
3287 | SBR4 | J06+ | J06 | General J06 | EZ - Breathing equipment (air breathing masks with portable bottle) for teams inside the ship out of lhe firefighter equipment to be evaluated. | Shipyard Certificate - STW EZ | 5 - Waiting Proof | 4 - Under Analysis | STW of EZ (EZ2C) and RIC with delivery of the masks to the crew. | Commissioning / PCP | STW do EZ (EZ2C) e RIC com a entrega das máscaras à tripulação.
3288 | SBR4 | J06+ | J06 | General J06 | EF - Detection onboard and firefighting (extinguishers, equipped fire fighter, breathing equipment) | Shipyard Certificate - STW EF | 5 - Waiting Proof | 5 - Waiting Proof | Validate through Section 10 of the Onboard Inspection + EF2C test. | Commissioning / Quality | Validar pela Seção 10 da Inspeção a Bordo + teste EF2C.
3289 | SBR4 | J06+ | J06 | General J06 | DA - Portable pumps to drain the bilges in case of leakage (forward and aft areas). | Shipyard Certificate - Evidence reference - RIC-xxxx | 5 - Waiting Proof | 4 - Under Analysis | Validated through Section 8 of the Onboard Inspection, or RIC stating it is onboard. | Quality (Onboard Inspection) | Validado pela Seção 8 da Inspeção a Bordo, ou RIC informando que está embarcado.
3290 | SBR4 | J06+ | J06 | General J06 | BT - Availability of partial subsystem BT power supply at least in 8350, auxiliary compartments (to supply portable pumps for instance). | Shipyard Certificate - STW BT | 5 - Waiting Proof | 4 - Under Analysis | Execute the BT1C test. Commissioning to issue. | Commissioning | Executar o teste BT1C. Comissionamento a emitir.
3291 | SBR4 | J06+ | J06 | General J06 | Set of tools onboard in case of leakage as a first intervention (mechanical, electricity, piping). | Shipyard Certificate - Evidence reference - RIC-xxxx | 5 - Waiting Proof | 5 - Waiting Proof | Commissioning to prepare RIC. Replicate the RIC from SBR3. Check folder. | Commissioning | Comissionamento a preparar o RIC. Replicar o RIC do SBR3. Verificar a pasta.
3292 | SBR4 | J06+ | J06 | General J06 | Safety and configuration of the deck (lifeline, "filiéres (spinneret)", sail's handrail) | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | 1 - Validated by ICN | Already validated by ICN. No further evidence required. | — (Closed – no pending) | Já validado pela ICN. Nenhuma evidência adicional necessária.
3293 | SBR4 | J06+ | J06 | General J06 | Set of individual safety means (including life jackets, safety harness). | Shipyard Certificate - RIC with the EPIs that will be used | 5 - Waiting Proof | 5 - Waiting Proof | RIC stating that the life jackets and safety harnesses will be provided by ICN. | Ship Manager | RIC informando que os coletes salva-vidas e cintos de segurança serão fornecidos pela ICN.
3294 | SBR4 | J06+ | J06 | General J06 | Power supply configuration: battery to be set up. | Shipyard Certificate - Evidence reference - RIC-xxxx | 5 - Waiting Proof | 4 - Under Analysis | Commissioning to replicate the RIC from SBR3. Check folder. | Commissioning | Comissionamento a replicar o RIC do SBR3. Verificar a pasta.
3295 | SBR4 | J06+ | J06 | General J06 | Safety drills to be organized by ICN as per the safety measures list. | Shipyard Certificate - Training report Checklist for controls and records - LV | 5 - Waiting Proof | 5 - Waiting Proof | List of trainings (CAV) carried out by SP. | SOP | Lista de treinamentos (CAV) realizados pela SP.
3298 | SBR4 | J06+ | J06 | General J06 | ICN procedures to be prepared: Transfer Main Hall to Ship lift, Undocking (in annex, the procedure will describe in ali the configurations how the ship can be undocked on decision of the dock master), Hauling and Mooring. | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | 1 - Validated by ICN | Already validated by ICN. No further evidence required. | — (Closed – no pending) | Já validado pela ICN. Nenhuma evidência adicional necessária.
3299 | SBR4 | J06+ | J06 | General J06 | ICN organization and responsibilities for the transfer and undocking, hauling, and mooring phases (teams, distribution onboard, who do what, safety cycling, registers, communication between onboard and quay, tug boats, divers ... ). | Shipyard Certificate - J06 Presentation of the briefing | 1 - Validated by ICN | 1 - Validated by ICN | Already validated by ICN. No further evidence required. | — (Closed – no pending) | Já validado pela ICN. Nenhuma evidência adicional necessária.
3306 | SBR4 | J06 | J06 | General J06 | Temporary instructions must be issued by ICN before every seaout | Shipyard Certificate - Temporary Instructions - J06 | 5 - Waiting Proof | 5 - Waiting Proof | To be done close to the last day of milestone crossing | Ship Manager | A ser feito próximo ao último dia da passagem do marco.

## Summary by Responsible
Open Items by Responsible (excludes closed: Validated / Not Blocking)
Responsible | Total | Blocking | Waiting/Other | Items
Ship Manager | 22 | 1 | 21 | 2, 613, 614, 616, 620, 621, 623, 638, 646, 667, 725, 736, 784, 1027, 1030, 3098, 3100, 3103, 3279, 3280, 3293, 3306
Commissioning | 10 | 1 | 9 | 409, 673, 718, 3095, 3096, 3109, 3278, 3290, 3291, 3294
Quality | 9 | 8 | 1 | 618, 619, 624, 660, 661, 733, 756, 1102, 1745
Production | 4 | 2 | 2 | 611, 622, 3281, 3282
NG (Naval Group) | 3 | 0 | 3 | 211, 560, 564
GTO | 3 | 0 | 3 | 405, 782, 3113
SOP | 2 | 0 | 2 | 3099, 3295
Quality (Onboard Inspection) | 2 | 0 | 2 | 3285, 3289
(To be assigned) | 1 | 1 | 0 | 676
PCP | 1 | 0 | 1 | 3111
Commissioning / PCP | 1 | 0 | 1 | 3287
Commissioning / Quality | 1 | 0 | 1 | 3288

## Status Changes
Mudanças de status (Anterior → Atual) — 39 item(ns)
Item | Status Anterior | Status Atual | Description
2 | 5 - Waiting Proof | 4 - Under Analysis | Broadcasting safety alarms to all rooms of the ship.
211 | 3 - Blocking | 4 - Under Analysis To Not Blocking | Electrolyte agitation circuit. Leak test.
409 | 5 - Waiting Proof | 4 - Under Analysis | Circuits subjected to submergence pressure Leak test
412 | 5 - Waiting Proof | 1 - Validated by ICN | Leak test. Circuits subjected to submergence Circuits subjected to submergence pressure.
426 | 5 - Waiting Proof | 1 - Validated by ICN | Circuits subjected to submergence pressure. Entire EM circuit
445 | 3 - Blocking | 1 - Validated by ICN | Circuits subjected to submergence pressure. Leak test of the draining circuit of tube
494 | 3 - Blocking | 1 - Validated by ICN | Leak test. Circuits subjected to submergence pressure.
605 | 4 - Under Analysis To Not Blocking | 2 - Not Blocking | Air renewal ventilation system : Configurations ventilation charts in battery rooms
647 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Penetration outfitting according to “Pressure Hull integrity” plan AC32004
648 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Penetration outfitting according to “Pressure Hull integrity” plan AC32005
649 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Penetration outfitting according to “Pressure Hull integrity” plan AC32006
650 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Penetration outfitting according to “Pressure Hull integrity” plan AC32007
651 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Penetration outfitting according to “Pressure Hull integrity” plan AC32008
652 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Penetration outfitting according to “Pressure Hull integrity” plan AC32009
654 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Penetration outfitting according to “Pressure Hull integrity” plan AC32011
658 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Penetration outfitting according to “Pressure Hull integrity” plan AC32015
676 | 1 - Validated by ICN | 3 - Blocking | Penetration outfitting according to “Pressure Hull integrity” plan AC32050 - Sanitary tank FQ00804
729 | 7 - Missing Vacuum Test or Sign | 1 - Validated by ICN | Penetration outfitting according to “Pressure Hull integrity” plan AC33043
764 | 4 - Under Analysis To Not Blocking | 2 - Not Blocking | Penetration outfitting according to “Pressure Hull integrity” plan AC34040
765 | 4 - Under Analysis To Not Blocking | 2 - Not Blocking | Penetration outfitting according to “Pressure Hull integrity” plan AC34041
779 | 5 - Waiting Proof | 1 - Validated by ICN | Safety device Sewage tank FQ
781 | 5 - Waiting Proof | 1 - Validated by ICN | Safety device Torpedo tubes KT
785 | 5 - Waiting Proof | 1 - Validated by ICN | Document to be produce by ICN in conformity with SOI, This includes specifically SOD_M2_CH_1-14 “Refloating”
809 | 5 - Waiting Proof | 1 - Validated by ICN | Functional test of the voice-activated telephone network
818 | 3 - Blocking | 1 - Validated by ICN | Leak pressure tests Forward air production and distribution line
855 | 4 - Under Analysis To Not Blocking | 2 - Not Blocking | Air renewal ventilation system: Setting Configurations
1723 | 5 - Waiting Proof | 1 - Validated by ICN | Circuits subjected to submergence pressure. Leak test
1737 | 3 - Blocking | 1 - Validated by ICN | Circuits subjected to submergence pressure. Leak test of the blowing air circuits
1741 | 3 - Blocking | 1 - Validated by ICN | Circuits subjected to submergence pressure. Leak test of the blowing air circuits
1745 | 3 - Blocking | 4 - Under Analysis | Circuits subjected to submergence pressure. LP and HP hydraulic circuits leak test
1761 | 5 - Waiting Proof | 1 - Validated by ICN | Circuits subjected to submergence pressure. Leak test of compress gas circuit of MultiCom Mast
1762 | 5 - Waiting Proof | 1 - Validated by ICN | Circuits subjected to submergence pressure. Leak test of compress gas circuit of ESM Mast
1763 | 5 - Waiting Proof | 1 - Validated by ICN | Circuits subjected to submergence pressure. Leak test of compress gas circuit of Radar Mast
3096 | 5 - Waiting Proof | 4 - Under Analysis | Safety equipment availability, good condition and use-by date validity – J01/J03 to J06 scope.
3109 | 5 - Waiting Proof | 4 - Under Analysis | Fresh water tank Nb 2 water level over low level (Supplying water mist)
3287 | 5 - Waiting Proof | 4 - Under Analysis | EZ - Breathing equipment (air breathing masks with portable bottle) for teams inside the ship out of lhe firefighter equipment to be evaluated.
3289 | 5 - Waiting Proof | 4 - Under Analysis | DA - Portable pumps to drain the bilges in case of leakage (forward and aft areas).
3290 | 5 - Waiting Proof | 4 - Under Analysis | BT - Availability of partial subsystem BT power supply at least in 8350, auxiliary compartments (to supply portable pumps for instance).
3294 | 5 - Waiting Proof | 4 - Under Analysis | Power supply configuration: battery to be set up.

## Item History
Histórico de status por item (Inicial → ... → Atual)
Item | Linha do tempo de status
2 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (27/07 10:42)
39 | 1 - Validated by ICN (Inicial)
49 | 1 - Validated by ICN (Inicial)
133 | 1 - Validated by ICN (Inicial)
207 | 2 - Not Blocking (Inicial)
208 | 1 - Validated by ICN (Inicial)
209 | 1 - Validated by ICN (Inicial)
211 | 3 - Blocking (Inicial) → 4 - Under Analysis To Not Blocking (28/07 08:25)
214 | 1 - Validated by ICN (Inicial)
243 | 1 - Validated by ICN (Inicial)
326 | 1 - Validated by ICN (Inicial)
405 | 5 - Waiting Proof (Inicial)
406 | 1 - Validated by ICN (Inicial)
407 | 1 - Validated by ICN (Inicial)
408 | 1 - Validated by ICN (Inicial)
409 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (28/07 08:25)
411 | 1 - Validated by ICN (Inicial)
412 | 5 - Waiting Proof (Inicial) → 1 - Validated by ICN (28/07 08:25)
415 | 1 - Validated by ICN (Inicial)
416 | 1 - Validated by ICN (Inicial)
417 | 1 - Validated by ICN (Inicial)
426 | 5 - Waiting Proof (Inicial) → 1 - Validated by ICN (27/07 10:42)
432 | 1 - Validated by ICN (Inicial)
434 | 1 - Validated by ICN (Inicial)
435 | 1 - Validated by ICN (Inicial)
436 | 1 - Validated by ICN (Inicial)
437 | 1 - Validated by ICN (Inicial)
438 | 1 - Validated by ICN (Inicial)
439 | 1 - Validated by ICN (Inicial)
442 | 1 - Validated by ICN (Inicial)
443 | 1 - Validated by ICN (Inicial)
445 | 3 - Blocking (Inicial) → 4 - Under Analysis (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
446 | 1 - Validated by ICN (Inicial)
447 | 1 - Validated by ICN (Inicial)
451 | 1 - Validated by ICN (Inicial)
461 | 1 - Validated by ICN (Inicial)
462 | 1 - Validated by ICN (Inicial)
463 | 1 - Validated by ICN (Inicial)
487 | 1 - Validated by ICN (Inicial)
494 | 3 - Blocking (Inicial) → 1 - Validated by ICN (28/07 08:25)
526 | 1 - Validated by ICN (Inicial)
528 | 2 - Not Blocking (Inicial)
560 | 4 - Under Analysis (Inicial)
564 | 4 - Under Analysis To Not Blocking (Inicial)
566 | 1 - Validated by ICN (Inicial)
570 | 1 - Validated by ICN (Inicial)
571 | 1 - Validated by ICN (Inicial)
575 | 1 - Validated by ICN (Inicial)
585 | 1 - Validated by ICN (Inicial)
605 | 4 - Under Analysis To Not Blocking (Inicial) → 2 - Not Blocking (28/07 08:25)
607 | 1 - Validated by ICN (Inicial)
609 | 1 - Validated by ICN (Inicial)
610 | 1 - Validated by ICN (Inicial)
611 | 3 - Blocking (Inicial)
612 | 2 - Not Blocking (Inicial)
613 | 7 - Missing Vacuum Test or Sign (Inicial)
614 | 7 - Missing Vacuum Test or Sign (Inicial)
616 | 7 - Missing Vacuum Test or Sign (Inicial)
618 | 3 - Blocking (Inicial)
619 | 3 - Blocking (Inicial)
620 | 7 - Missing Vacuum Test or Sign (Inicial)
621 | 7 - Missing Vacuum Test or Sign (Inicial)
622 | 3 - Blocking (Inicial)
623 | 7 - Missing Vacuum Test or Sign (Inicial)
624 | 3 - Blocking (Inicial)
625 | 1 - Validated by ICN (Inicial)
626 | 1 - Validated by ICN (Inicial)
627 | 1 - Validated by ICN (Inicial)
628 | 1 - Validated by ICN (Inicial)
629 | 1 - Validated by ICN (Inicial)
636 | 1 - Validated by ICN (Inicial)
638 | 7 - Missing Vacuum Test or Sign (Inicial)
645 | 1 - Validated by ICN (Inicial)
646 | 7 - Missing Vacuum Test or Sign (Inicial)
647 | 7 - Missing Vacuum Test or Sign (Inicial) → 6 - Waiting B05 (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
648 | 7 - Missing Vacuum Test or Sign (Inicial) → 6 - Waiting B05 (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
649 | 7 - Missing Vacuum Test or Sign (Inicial) → 6 - Waiting B05 (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
650 | 7 - Missing Vacuum Test or Sign (Inicial) → 6 - Waiting B05 (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
651 | 7 - Missing Vacuum Test or Sign (Inicial) → 6 - Waiting B05 (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
652 | 7 - Missing Vacuum Test or Sign (Inicial) → 6 - Waiting B05 (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
653 | 1 - Validated by ICN (Inicial)
654 | 7 - Missing Vacuum Test or Sign (Inicial) → 6 - Waiting B05 (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
655 | 1 - Validated by ICN (Inicial)
657 | 1 - Validated by ICN (Inicial)
658 | 7 - Missing Vacuum Test or Sign (Inicial) → 6 - Waiting B05 (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
660 | 3 - Blocking (Inicial)
661 | 3 - Blocking (Inicial)
667 | 7 - Missing Vacuum Test or Sign (Inicial)
673 | 3 - Blocking (Inicial)
676 | 1 - Validated by ICN (Inicial) → 3 - Blocking (28/07 08:25)
704 | 1 - Validated by ICN (Inicial)
705 | 1 - Validated by ICN (Inicial)
706 | 1 - Validated by ICN (Inicial)
708 | 1 - Validated by ICN (Inicial)
711 | 1 - Validated by ICN (Inicial)
714 | 1 - Validated by ICN (Inicial)
718 | 7 - Missing Vacuum Test or Sign (Inicial)
719 | 1 - Validated by ICN (Inicial)
725 | 7 - Missing Vacuum Test or Sign (Inicial)
729 | 7 - Missing Vacuum Test or Sign (Inicial) → 6 - Waiting B05 (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
730 | 1 - Validated by ICN (Inicial)
732 | 2 - Not Blocking (Inicial)
733 | 3 - Blocking (Inicial)
736 | 7 - Missing Vacuum Test or Sign (Inicial)
743 | 1 - Validated by ICN (Inicial)
751 | 1 - Validated by ICN (Inicial)
752 | 1 - Validated by ICN (Inicial)
756 | 3 - Blocking (Inicial)
764 | 4 - Under Analysis To Not Blocking (Inicial) → 2 - Not Blocking (27/07 10:42)
765 | 4 - Under Analysis To Not Blocking (Inicial) → 2 - Not Blocking (27/07 10:42)
777 | 1 - Validated by ICN (Inicial)
779 | 5 - Waiting Proof (Inicial) → 1 - Validated by ICN (28/07 08:25)
780 | 1 - Validated by ICN (Inicial)
781 | 5 - Waiting Proof (Inicial) → 1 - Validated by ICN (28/07 08:25)
782 | 5 - Waiting Proof (Inicial)
783 | 1 - Validated by ICN (Inicial)
784 | 5 - Waiting Proof (Inicial)
785 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
786 | 1 - Validated by ICN (Inicial)
809 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
817 | 1 - Validated by ICN (Inicial)
818 | 3 - Blocking (Inicial) → 1 - Validated by ICN (28/07 08:25)
820 | 1 - Validated by ICN (Inicial)
822 | 1 - Validated by ICN (Inicial)
840 | 1 - Validated by ICN (Inicial)
855 | 4 - Under Analysis To Not Blocking (Inicial) → 2 - Not Blocking (27/07 10:42)
1006 | 1 - Validated by ICN (Inicial)
1007 | 1 - Validated by ICN (Inicial)
1008 | 1 - Validated by ICN (Inicial)
1009 | 1 - Validated by ICN (Inicial)
1010 | 1 - Validated by ICN (Inicial)
1012 | 1 - Validated by ICN (Inicial)
1014 | 1 - Validated by ICN (Inicial)
1022 | 1 - Validated by ICN (Inicial)
1025 | 1 - Validated by ICN (Inicial)
1026 | 1 - Validated by ICN (Inicial)
1027 | 3 - Blocking (Inicial)
1029 | 1 - Validated by ICN (Inicial)
1030 | 5 - Waiting Proof (Inicial)
1102 | 3 - Blocking (Inicial)
1110 | 1 - Validated by ICN (Inicial)
1193 | 1 - Validated by ICN (Inicial)
1576 | 1 - Validated by ICN (Inicial)
1618 | 1 - Validated by ICN (Inicial)
1619 | 1 - Validated by ICN (Inicial)
1620 | 1 - Validated by ICN (Inicial)
1621 | 1 - Validated by ICN (Inicial)
1723 | 5 - Waiting Proof (Inicial) → 1 - Validated by ICN (28/07 08:25)
1724 | 1 - Validated by ICN (Inicial)
1726 | 1 - Validated by ICN (Inicial)
1731 | 1 - Validated by ICN (Inicial)
1732 | 1 - Validated by ICN (Inicial)
1733 | 1 - Validated by ICN (Inicial)
1734 | 1 - Validated by ICN (Inicial)
1735 | 1 - Validated by ICN (Inicial)
1736 | 1 - Validated by ICN (Inicial)
1737 | 3 - Blocking (Inicial) → 1 - Validated by ICN (28/07 08:25)
1738 | 1 - Validated by ICN (Inicial)
1739 | 1 - Validated by ICN (Inicial)
1740 | 1 - Validated by ICN (Inicial)
1741 | 3 - Blocking (Inicial) → 4 - Under Analysis (27/07 10:42) → 1 - Validated by ICN (28/07 08:25)
1744 | 1 - Validated by ICN (Inicial)
1745 | 3 - Blocking (Inicial) → 4 - Under Analysis (28/07 08:25)
1746 | 1 - Validated by ICN (Inicial)
1747 | 1 - Validated by ICN (Inicial)
1748 | 1 - Validated by ICN (Inicial)
1749 | 1 - Validated by ICN (Inicial)
1750 | 1 - Validated by ICN (Inicial)
1751 | 1 - Validated by ICN (Inicial)
1752 | 1 - Validated by ICN (Inicial)
1753 | 1 - Validated by ICN (Inicial)
1754 | 1 - Validated by ICN (Inicial)
1755 | 1 - Validated by ICN (Inicial)
1758 | 1 - Validated by ICN (Inicial)
1759 | 1 - Validated by ICN (Inicial)
1760 | 1 - Validated by ICN (Inicial)
1761 | 5 - Waiting Proof (Inicial) → 1 - Validated by ICN (27/07 10:42)
1762 | 5 - Waiting Proof (Inicial) → 1 - Validated by ICN (27/07 10:42)
1763 | 5 - Waiting Proof (Inicial) → 1 - Validated by ICN (27/07 10:42)
1764 | 1 - Validated by ICN (Inicial)
1765 | 1 - Validated by ICN (Inicial)
3005 | 1 - Validated by ICN (Inicial)
3095 | 5 - Waiting Proof (Inicial)
3096 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (28/07 08:25)
3097 | 1 - Validated by ICN (Inicial)
3098 | 5 - Waiting Proof (Inicial)
3099 | 5 - Waiting Proof (Inicial)
3100 | 5 - Waiting Proof (Inicial)
3101 | 1 - Validated by ICN (Inicial)
3102 | 2 - Not Blocking (Inicial)
3103 | 5 - Waiting Proof (Inicial)
3105 | 1 - Validated by ICN (Inicial)
3106 | 1 - Validated by ICN (Inicial)
3107 | 1 - Validated by ICN (Inicial)
3109 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (28/07 08:25)
3111 | 5 - Waiting Proof (Inicial)
3113 | 5 - Waiting Proof (Inicial)
3277 | 1 - Validated by ICN (Inicial)
3278 | 5 - Waiting Proof (Inicial)
3279 | 5 - Waiting Proof (Inicial)
3280 | 5 - Waiting Proof (Inicial)
3281 | 5 - Waiting Proof (Inicial)
3282 | 5 - Waiting Proof (Inicial)
3284 | 1 - Validated by ICN (Inicial)
3285 | 5 - Waiting Proof (Inicial)
3286 | 1 - Validated by ICN (Inicial)
3287 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (27/07 10:42)
3288 | 5 - Waiting Proof (Inicial)
3289 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (28/07 08:25)
3290 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (28/07 08:25)
3291 | 5 - Waiting Proof (Inicial)
3292 | 1 - Validated by ICN (Inicial)
3293 | 5 - Waiting Proof (Inicial)
3294 | 5 - Waiting Proof (Inicial) → 4 - Under Analysis (28/07 08:25)
3295 | 5 - Waiting Proof (Inicial)
3298 | 1 - Validated by ICN (Inicial)
3299 | 1 - Validated by ICN (Inicial)
3306 | 5 - Waiting Proof (Inicial)